07Jul

======================================================================

Minutes of Meeting (MoM)

Connection Enhancement Program – Requirement Workshop (Scope Alignment) Date: 07 July 2026

Key Discussion Points

- Requirement workshops initiated to clarify CX requirements, user journeys, task flows, design considerations, and implementation feasibility.

- Multi-Leg / Unified Boarding Pass identified as the primary feature for discussion.

- Unified Boarding Pass has been proposed for Phase-1 delivery, subject to leadership alignment and feasibility assessment.

- Cross-functional teams reviewed business, airport operations, AOCS, PSS, product, design, and technology implications.

- Multiple operational dependencies were identified around:

  - Sequence numbers for each flight leg

  - SSR handling

  - Boarding pass perforation/stub requirements

  - QR code feasibility

  - Airport scanner compatibility

  - Boarding pass layout constraints

  - Regulatory and operational approvals

Ownership & Approval Matrix

| Area | Owner(s) | Responsibility |
| --- | --- | --- |
| CX Requirement Sign-off | Naresh Rao, Summi Sharma | Final business requirement approval |
| Product Ownership | Swati Kothiyal, Rajat Upreti, Nihardip Sharma | Product governance, prioritization, requirement alignment |
| Design & UX | Shreenivas S. Ranasubhe, Gunjan Mathur, Prayas, Ishika Verma | User flows, boarding pass design, prototypes |
| Airport & CX Business | Heena Malhotra, Naresh Rao, Raja Karmakar | Business requirements and operational approvals |
| AOCS (Digital) AOCS (Business) | Kshitij Khshtarpal, Mohit Goyal, Randhir Chambail Gaurav Malhotra, Prativa Biswal, Mansi Negi | Operational feasibility, boarding validation, airport process impacts |
| PSS | Sachin Kumar, Purnima | Boarding pass generation, barcode and QR feasibility |
| Salesforce / Data | Mayank Tyagi, Lakshmi Gopalkrishnan | Platform feasibility and integration assessment |
| Development & Architecture | Subham Srivastava | Technical architecture and implementation approach |
| Testing Lead | Vishal, Brian | End-to-end validation and operational testing |

Decisions Taken

| # | Decision | Owner |
| --- | --- | --- |
| 1 | Unified Boarding Pass to be assessed for inclusion in Phase-1. | CX Business |
| 2 | Connecting Journey Tag is a mandatory boarding pass element. | Airport, CX Business |
| 3 | Trip Member details are mandatory. | Airport, CX Business |
| 4 | Sequence numbers for both flight legs must be displayed. | AOCS (Digital) |
| 5 | SSR information cannot be removed from boarding passes. | AOCS (Digital)/ Airport Operations |
| 6 | Boarding pass design must support operational stubbing/perforation requirements. | AOCS (Digital) / Design |
| 7 | Feasibility of single QR code for multiple legs requires technical validation. | PSS , AOCS, CX Business |
| 8 | Airport scanner compatibility must be validated before finalizing QR solution. | PSS , AOCS, CX Business |

Action Items

| Action Item | Owner | Support Team | Priority |
| --- | --- | --- | --- |
| Finalize ownership and sign-off matrix for all features. | Swati Kothiyal | CX, Airport Teams, Product, PSS, AOCS, Design | High |
| Produce detailed Unified Boarding Pass design options. | Shreenivas S. Ranasubhe | Product, Airport Ops | High |
| Define mandatory vs optional boarding pass fields. | Heena Malhotra | AOCS, PSS | High |
| Validate sequence number handling for both flight legs. | Mohit Goyal, Kshitij | PSS | High |
| Assess feasibility of single QR code covering multiple legs. | Randhir Chambail, Vinay Yadav | PSS, AOCS | High |
| Confirm airport infrastructure compatibility with 2D QR codes. | Sachin Kumar | Airport Operations | High |
| Obtain Air France/KLM/Etihad boarding pass examples with scannable barcode quality. | Sachin Kumar | PSS | Medium |
| Validate SSR display requirements and space constraints. | Alka Kumari, Akshita Paul | Design Team | High |
| Review boarding pass stub/perforation requirements across domestic and international stations. | Mohit Goyal | Airport Operations | High |
| Prepare timeline estimate for Phase-1 and Phase-2 items for leadership review. | Swati Kothiyal, Rajat Upreti | Design, Tech, CX, AOCS, PSS | High |
| Conduct airport testing once QR feasibility solution is available. | Heena Malhotra, Brian | PSS, Airport Ops | High |

Risks & Open Questions

| Open Item | Owner |
| --- | --- |
| Can one QR code support both flight legs without operational impact? | PSS / AOCS |
| Will airport scanners and gate devices support new QR format? | PSS |
| How will boarding pass information be accommodated within size constraints? | Design Team |
| How will boarding pass data remain accurate if downstream flights are delayed? | CX / Airport Operations |
| How should SSR information for multiple legs be displayed? | AOCS / PSS |
| What approval, compliance, and regulatory checks are required prior to rollout? | Airport Operations & CX Team |

Summary

The workshop established ownership across Product, CX, Design, AOCS, PSS, Airport Operations, and Development teams. The primary focus was the Unified Boarding Pass feature.

While business teams confirmed the mandatory information required on the boarding pass, several feasibility assessments remain open, particularly around QR code implementation, scanner compatibility, SSR handling, and operational boarding pass validation. A detailed design and technical assessment will be completed before final commitment into Phase-1 delivery.

08Jul- MoM

Please find below the Minutes of Meeting (MoM):

Meeting Objective

Review Phase 1 and Phase 2 scope, align delivery timelines, discuss technical feasibility and dependencies, and prepare inputs for the leadership review.

Key Discussion Points

1. Phase 1 (0–3 Months) – Quick Wins

The following items were reviewed as Phase 1 deliverables:

- Date Change Indicator on Website & App

- Total Journey Banner

- Single Web Check-in enhancement for connecting flights

- Static Airport Maps & Terminal Transfer Guide

- BlueChip Identification on Boarding Pass

- Initial boarding pass design improvements

Discussion Points

- Single Web Check-in requires additional validation for 48-hour connection scenarios.

- Static Airport Maps and Terminal Transfer Guide remain dependent on PSS feasibility and data availability.

- Design team highlighted bandwidth constraints and advised that all initiatives cannot run fully in parallel.

- Timelines presented are indicative and subject to dependency and approval closures.

2. Phase 2 (3–6 Months) – Advanced Capabilities

The following items were proposed under Phase 2:

- Unified Boarding Pass

- Live Baggage Tracking

- Operational Connection Monitoring

- Automated Misconnection Recovery

- Internal Monitoring Dashboard (CX & Airport Teams)

- Gate/Belt Push Notifications

Discussion Points

- Operational Connection Monitoring will leverage Kafka event streams, MCT tables, ETA/ETD data, and Solution Tech logic.

- OCC representative (Vijender) will be engaged to validate data points and operational workflows.

- Additional workshop required with OCC, Network Planning, CX and Design teams.

3. Live Baggage Tracking – Feasibility Review

Detailed discussion was conducted with Digital and Innovation teams.

Key Outcomes

- Technical capability exists to track baggage events through Kafka-based integrations.

- Current visibility is limited to airports where IndiGo BRS capabilities are available.

- Additional scanning touchpoints can be enabled subject to AOCS operational approval.

- MVP approach preferred for Phase 1.

Proposed Initial Customer Touchpoints

- Bag Checked-in

- Bag Transferred to Connecting Flight

- Bag Loaded on Flight

- Bag Arrived at Destination Belt

Dependencies

- AOCS manpower and process readiness

- Hardware/sensor deployment and POC completion

- Leadership approval for operational changes

4. Baggage Tracking POC

- Vendor to perform airport measurements and hardware assessment next week.

- Estimated POC preparation timeline: approximately 15–20 days post assessment.

- Weekly review cadence to be established for POC progress tracking.

- Vinay/Randhir team to share event definitions, technical feasibility details and proposed solution approach.

5. Unified Boarding Pass Discussion

Multiple boarding pass concepts were reviewed.

Key Decisions

- Two design options will be explored:

  - Dual Barcode Model (one barcode per leg)

  - Single Barcode Model (all journey information in one barcode)

Inputs Required

- Mandatory boarding pass fields from AOCS/Operations.

- Regulatory and BCAS compliance requirements.

- Sample boarding passes from other airlines supporting multi-sector journeys.

- Barcode feasibility assessment by PSS team.

Feedback Received

- SSR information must remain visible on the passenger section of the boarding pass.

- Readability of all passenger information must be maintained.

- Business, BlueChip and loyalty-related information must be accommodated.

- Airport Operations team to provide field-wise validation and boarding pass requirements.

Action Items

| Action Item | Owner | Timeline |
| --- | --- | --- |
| Finalize and present Phase 1 & Phase 2 roadmap for leadership review | Heena / Swati | Immediate |
| Share updated baggage tracking feasibility and event details | Vinay / Randhir | Next Working Day |
| Arrange OCC workshop with Vijender and Network Planning team | Heena | Tomorrow (09Jul) |
| Define operational connection monitoring data points | OCC + CX + Digital | Workshop Session |
| Share mandatory boarding pass field requirements | AOCS Team (Akshita/Alka/Kshitij) | ASAP |
| Share sample multi-sector boarding passes from other airlines | AOCS Team (Akshita/Alka/Kshitij) | ASAP |
| Conduct barcode feasibility assessment | Sachin (PSS) | Post receipt of samples |
| Track baggage POC progress through recurring reviews | Swati / Subham / Vinay | Weekly |
| Consolidate feature-wise dependencies and approvals | Prayas / Swati | Ongoing |

Risks & Dependencies

- PSS feasibility for airport maps and transfer guide.

- AOCS approval and operational buy-in for baggage tracking enhancements.

- Availability of real-time event feeds and simulation environments.

- Design bandwidth constraints across multiple concurrent initiatives.

- Regulatory and boarding pass compliance approvals.

Next Steps

- Continue requirement workshops feature-by-feature.

- Review dependencies, approvals and technical feasibility in daily cadence.

- Present phased roadmap, timelines and identified dependencies to leadership.

- Conduct in-person workshop with all required stakeholders for detailed requirement finalization.

==========================================================================================================================================================

Additionally, please note that the final implementation timelines, along with specific dates, can only be shared after:

- Detailed discussions on the Phase 1 and Phase 2 scope are completed.

- Analysis and POCs are finalized by the respective teams, accordingly the design team shares the final wireframes.

09Jul – MoM

Executive Summary

The workshop focused on:

- Finalization of Release-wise delivery approach.

- Validation of dependencies for Phase 1 and Release 1 features.

- Identification of technical and operational dependencies for:

  - Unified Boarding Pass

  - Static Airport Maps

  - Connection Notifications

  - Operations Dashboard

  - Gate & Baggage Information

- Alignment on ownership and workshop cadence.

- Acceleration of key customer-facing capabilities into Phase 1 / August release.

Key Decisions

| Item | Decision |
| --- | --- |
| Delivery Approach | Program to be tracked release-wise instead of phase-wise only |
| DSM Cadence | Dedicated DSM to track feature-level progress and blockers |
| Connection Notifications | Moved to August release (earlier than planned) |
| Operations Dashboard | Advanced to August release; workshop required immediately |
| Airport Maps | Prefer Airport API integration over static image storage approach |
| Unified Boarding Pass | Requires joint alignment between PSS, CX and Digital |
| Baggage Belt Information | Feasibility to be assessed using Navitaire "Baggage Reclaim" field |
| Single Source of Truth | Navitaire to be primary source wherever possible |

Discussion Summary by Feature

1. Date Change Indicator

Discussion

- Existing Kafka event framework may support this functionality.

- Validation required on data source and dependency on PSS.

- Need detailed review of scenarios.

Outcome

- Digital team to review Kafka event mechanism.

- PSS to validate if additional integration support is required.

2. Static Airport Maps

Discussion

- Static storage approach was discussed.

- CX recommended dynamic airport map updates through Airport APIs.

- Concern raised regarding outdated maps if maintained manually.

Outcome

- Airport API integration preferred.

- AOCS to support API assessment.

3. Connection Status Notifications

Discussion

- Customer notifications identified as critical.

- Business requested acceleration.

Outcome

Moved to August Release.

4. Operations Dashboard

Discussion

- Dashboard considered critical for disruption handling.

- Wireframe and requirements workshop required.

Outcome

- Dashboard delivery advanced to August.

- Joint workshop mandated.

5. Gate & Baggage Belt Information

Discussion

- Gate information exists in Navitaire.

- Baggage belt information not currently available.

- Aditya identified "Baggage Reclaim" field in Navitaire that may support the requirement.

- Manual update process needs assessment.

Outcome

- Technical feasibility review required.

- Single-source architecture preferred.

6. Unified Boarding Pass

Discussion

- Requirement to display:

  - BluChip Tier

  - Heart identifier

  - Consistent boarding pass experience across channels

Concerns

- Airport-operated kiosks may not support all enhancements.

- Feasibility depends on PSS pack templates and external kiosk capabilities.

Outcome

- CX, PSS and Digital including Design Team alignment workshop required.

- Detailed requirement walkthrough to be scheduled.

7. BluChip Tier reflecting on Boarding Pass

Discussion

- Design and data feasibility to be reviewed.

Outcome

- Design team will share wireframes for approval.

Action Tracker

| # | Action Item | Owner | Supporting Teams | Timeline | Dependency | Risk |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Start DSM governance and weekly feature tracking | Swati Kothiyal | All SPOCs | Immediate (11 Jul 2026) | SPOC availability | Low |
| 2 | Finalize Release 1 feature-level delivery plan | Subham | Delivery Team | 15 Jul 2026 | Requirement sign-off | Medium |
| 3 | Validate Kafka event solution for Date Change Indicator | Nihardip / Digital Team | PSS | 18 Jul 2026 | Kafka event availability | Medium |
| 4 | Conduct detailed review of Date Change Indicator scenarios | Sachin Kumar | Digital | 16 Jul 2026 | Requirement clarity | Medium |
| 5 | Assess Airport API availability for airport maps | Aditya Singh (AOCS) | PSS, Airport Ops | 18 Jul 2026 | Airport vendors | High |
| 6 | Finalize Airport Maps implementation approach | Randhir / Digital | CX,PSS, AOCS | 22 Jul 2026 | API assessment | High |
| 7 | Bring Connection Notification feature into August release plan | Arshpreet Narang | Digital, Solution Tek Team | 15 Jul 2026 | Notification platform readiness | Medium |
| 8 | Conduct notification implementation workshop | Swati | Ashpreet, Gulshan, Aditya | 17 Jul 2026 | Stakeholder availability | Medium |
| 9 | Prepare Dashboard wireframe | Raja Karmakar | Mayank | 18 Jul 2026 | Dashboard requirements | Medium |
| 10 | Conduct Operations Dashboard workshop | Swati | Lakshmi, Charu, Mayank, PRISM Team, CX | 21 Jul 2026 | Wireframe completion | Medium |
| 11 | Evaluate Navitaire "Baggage Reclaim" field usage | Randhir Chambail | Aditya Singh, PSS | 18 Jul 2026 | Navitaire feasibility | High |
| 12 | Define solution for Gate and Baggage Belt Information | Digital & AOCS | PSS | 24 Jul 2026 | Data source confirmation | High |
| 13 | Organize Unified Boarding Pass workshop | Swati, Shreenivas | CX, PSS, Digital | 16 Jul 2026 | Business alignment | High |
| 14 | Share boarding pass design samples | Alka Kumari | CX Team | 11 Jul 2026 | Sample availability | Medium |
| 15 | Validate boarding pass printing feasibility across kiosks and channels | Sachin Kumar | PSS, Airport Partners | 25 Jul 2026 | External kiosk providers | High |
| 16 | Review BluChip Tier and Heart display requirements | Sachin Kumar | Loyalty, CIAM, CX | 22 Jul 2026 | Loyalty data availability | High |
| 17 | Identify CIAM/Loyalty system integration requirements | Loyalty Team | Digital, CX | 25 Jul 2026 | Data mapping | High |
| 18 | Capture all program-level blockers and risks in DSM tracker | Swati Kothiyal | PMO | Ongoing | Cross-functional inputs | Medium |
| 19 | Finalize Phase 1 scope and sign-off | CX Business Team (Heena/Raja) | Digital, AOCS | 31 Jul 2026 | Workshop outputs | High |
| 20 | Publish consolidated dependency tracker | PMO / Swati | All Workstream Leads | 18 Jul 2026 | SPOC inputs | Medium |

Upcoming Milestones

| Milestone | Target Date |
| --- | --- |
| Requirement Workshop Closure | 10 Jul 2026 |
| Solution Finalization | Week of 27 Jul 2026 |
| Release-1 Build Planning | Aug 2026 |
| Connection Notification Delivery | Aug 2026 |
| Operations Dashboard Delivery | Aug 2026 |
| Release 1 Go-Live | 25 Sep 2026 |
| Release 2 Go-Live | 25 Nov 2026 |
| Release 3 Go-Live | 31 Dec 2026 |

Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Airport API dependency | Delay in maps, gate and baggage features | Early AOCS & PSS engagement |
| Navitaire integration limitations | Boarding pass enhancements delayed | Early feasibility review with PSS |
| Boarding Pass Design | BluChip rollout delay | Engagement of CX and Loyalty on the BluChip details |
| Multiple external airport systems | Inconsistent customer experience | Standardized integration strategy |
| Manual baggage data updates | Data accuracy issues | Automation assessment using Navitaire fields |

======================================================================================================================================

Multiple cross-functional dependencies (PSS, AOCS, Airport APIs, Loyalty, Solution Tech) require closure before solution finalization.

However, Phase 1 scope and delivery dates remain achievable with weekly DSM governance and expedited workshops.

10Jul2026

Minutes of Meeting (MoM)

Connection Enhancement Program – Scope Alignment & Requirement Workshop

Date: 10 July 2026

Executive Summary

The workshop focused on finalizing Phase-1 scope, design dependencies, boarding pass requirements, connection disruption management, notification strategy, airport maps, and timeline alignment for achieving the first Connection Enhancement Program release targeted for 25 August 2026 and critical operational capabilities before 31 December 2026.

Key Decisions

- Real-time connection delay alerts and notifications to be included in Phase-1.

- Internal Connection Dashboard and Missed Connection / At-Risk Journey Management moved from Phase-2 to Phase-1 with target delivery before the disruption season.

- Static Airport Maps approved for initial implementation due to cost considerations; dynamic maps to be evaluated as a future enhancement.

- Unified/Connecting Boarding Pass remains dependent on leadership approval and operational feasibility discussions.

- Design work to proceed in parallel while pending operational decisions are escalated.

Major Discussion Points

1. Phase-1 Scope Enhancement

Leadership directed that the following be treated as critical Phase-1 deliverables:

- Connection Delay Notifications

- Real-Time Connection Alerts

- Connection Risk Journey Flow

- Missed Connection Management

- Internal Operations Dashboard

- Timeline-Based Passenger Journey Experience

Target Date: Before IROP season (31-Oct-2026)

2. Connection Disruption Management

Discussion

The end-to-end disruption handling experience will require integration with the Solution Tech platform to enable:

- Alternate Flight Recommendations

- Hotel Suggestions

- Passenger Protection Journey

- Missed Connection Recovery Flows

Dependency

Solution Tech Team (Salil / Amar team) to be onboarded.

3. Unified / Connection Boarding Pass

Key Concerns Raised

- Stretch vs Economy identification.

- Fast Forward entitlement visibility.

- Lounge eligibility identification.

- Upgrade journeys across connecting sectors.

- Ground staff visibility and servicing implications.

- Boarding pass scalability for future phases.

Open Leadership Decisions Required

- How to identify Stretch customers in a unified boarding pass.

- Handling mixed cabin itineraries.

- Upgrade entitlement management.

- Ground operations readiness.

- Transit upgrade scenarios.

These items require CX, Airport Operations and Leadership approval before finalization.

2 wireframe options Design team has shared.

5. Airport Maps

Current Direction

Phase-1 will include:

- Static airport maps

- Airport map access points within app journey

Future Consideration

- Dynamic maps

- Airport APIs

- Directional guidance

- Location-aware navigation

Owner from Airport Operations team (Aditya/Gaurav team) to provide airport integration inputs.

Action Tracker

| ID | Action Item | Owner | Target Date | Dependency | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Share 54 KPI metrics, supporting slides and Excel | Mayank Tyagi | 13-Jul-2026 | None | Open |
| 2 | Add Connection Delay Alerts and Real-Time Notifications to Phase-1 scope | Subham Srivastava | 13-Jul-2026 | Leadership direction | Open |
| 3 | Share Hub & Spoke requirements, website screenshots, FAQs and process document (Not a part of this project) | Brain Victor Solomon | 14-Jul-2026 | CX inputs | Open |
| 4 | Share Air India implementation benchmarks and comparison | Heena Malhotra | 14-Jul-2026 | Internal review | Open |
| 5 | Organize Solution Tech integration workshop | Swati Kothiyal | 14-Jul-2026 | Salil, Amar team availability | Open |
| 6 | Finalize disruption management approach and recovery flows | Heena Malhotra / Subham Srivastava | 18-Jul-2026 | Solution Tech workshop | Open |
| 7 | Share boarding pass design questions and assumptions | Shreenivas Ransubhe | 11-Jul-2026 | None | Open |
| 8 | Obtain leadership clarification on Stretch/Economy unified boarding pass scenarios | Swati Kothiyal | 18-Jul-2026 | CX, Airport Ops leadership | Open |
| 9 | Validate upgrade and entitlement scenarios for connecting journeys | Airport Operations Team | 18-Jul-2026 | Leadership inputs | Open |
| 10 | Share Date Change Indicator user stories in CEP Board | Swati Kothiyal | 13-Jul-2026 | None | In Progress |
| 11 | Complete Date Change Indicator wireframes | Shreenivas Ransubhe | 16-Jul-2026 | Stories & requirements | Planned |
| 12 | Complete Journey Duration Banner wireframes | Shreenivas Ransubhe | 16-Jul-2026 | Requirements freeze | Planned |
| 13 | Review designs with leadership and CX team | Heena Malhotra, Raja Karmakar | 17-Jul-2026 | Design delivery | Planned |
| 14 | Identify static airport map integration ownership and API feasibility | Aditya / Airport Operations Team | 18-Jul-2026 | Airport Systems team | Open |
| 15 | Collect complaint data related to auto check-in seat allocation failures | Heena Malhotra | 22-Jul-2026 | Customer complaint data | Open |
| 16 | Provide Phoenix user stories and acceptance criteria to Design | Nihardip Sharma / Prayas | 15-Jul-2026 | Phoenix backlog | Open |

Timeline Commitments Agreed

| Deliverable | Owner | Timeline |
| --- | --- | --- |
| Date Change Indicator Design | Shreenivas | 16-Jul-2026 |
| Journey Duration Banner Design | Shreenivas | 16-Jul-2026 |
| Design Leadership Review | CX & Design Teams | 17-Jul-2026 |
| Solution Tech Alignment Workshop | Swati | 14-Jul-2026 |
| Boarding Pass Clarification Questions | Shreenivas | Immediate |
| Airport Maps Ownership Confirmation | Airport Ops Team | 18-Jul-2026 |
| Connection Journey & Disruption Logic Review | Solution Tech + CX | Week of 13-Jul-2026 |
| Critical Phase-1 Planning Baseline | Digital Team | 25-Aug-2026 Go-Live Target |
| Internal Dashboard & Risk Connection Flow | Program Team | 25-Aug-2026 |

Risks Identified

| Risk | Impact | Owner |
| --- | --- | --- |
| Unified Boarding Pass operational feasibility unresolved | High | CX + Airport Ops |
| Stretch/Economy entitlement conflicts | High | Airport Ops |
| Solution Tech dependency for disruption handling | High | Digital |
| API integration dependency for airport maps | Medium | Airport Ops |
| Notification trigger approval pending | Medium | CX Leadership |
| Auto check-in seat assignment failures impacting customer experience | Medium | Digital + Operations |

Next Steps (Priority Order)

High Priority (Immediate)

- Onboard Solution Tech team for disruption management workshops.

- Finalize Phase-1 scope changes and leadership-approved features.

- Complete boarding pass clarification discussions.

- Deliver initial wireframes by 16-Jul-2026.

- Prepare leadership review session on 16-Jul-2026.