## Sheet1
S.No | Epic Name | Owner | Primary Dependencies | Dependent Teams | Digital & Buisness SPOC | Release | Target Release Date | Comments | NPRM Team | Target Achieved Yes/No | Design Team Target Date | Target Achieved Yes/No | PSS Target Date | Target Achieved Yes/No | AOCS Digital Target Date | Target Achieved Yes/No | Salesforce Target Date | Target Achieved Yes/No
1 | Date Change Indicators | Subham Srivastava | PSS Itinerary Data, Kafka Events, UX Design | PSS, Digital | Sachin | R1 | 2026-08-25 | Subham & Prayas will have a meeting today to discuss on the feedback |  |  | 2026-07-16 | Yes
2 | Journey Duration Banner | Subham Srivastava | Schedule Data, OCC Data, Network/PSS Data | OCC, Network, PSS | Sachin | R1 | 2026-08-25 |  |  |  | 2026-07-20
3 | Single Web Check-In | Subham Srivastava | PSS, DCS Rules, Droid Service | PSS, Airport Ops | Sachin | R1 | 2026-08-25 |  |  |  | 2026-07-21
4 | Static Airport Maps & Transfer Guidance | Aditya Singh, Heena | Airport Content, Airport APIs Validation | AOCS, Airport Ops | Vinay Yadav, Randhir | R1 | 2026-08-25 | Map API needs to be procured by respective Airport manager for authenticity As per Vinay POC needs to be done and single airport needs to be selected. API compatibility needs to be checked. |  |  | 2026-07-22
5 | Timeline Journey View P1 - Step-by-step journey, check-in, Boarding Pass | Subham Srivastava | UX Design, PSS APIs, AOCS Inputs | CX, Design, PSS | Sachin, Heena, Gaurav Malhotra | R1 | 2026-08-25 |  |  |  | 2026-07-24
6 | Connection status notifications | Lakshmi | NetOps Feed, Rules Engine, Notification Platform | NetOps, Digital | Mayank Tyagi | R1 | 2026-08-25
7 | Operations Dashboard | Lakshmi | Operational data sources, OCC, flight and airport feeds |  | Mayank Tyagi | R1 | 2026-08-25 | 1. Follow-up meeting with PRISM, Solution tek for requirements. Monday will
8 | BluChip BLU1/2/3 + Heart (Digital) and Physical | Loyalty Team | Loyalty Platform, CRM, CIAM, Capillary | Loyalty, CRM | Vikas Yadav | R1 | 2026-08-25 |  |  |  | 2026-07-31
9 | Connection Disruption Management | Salil Seth | Digital/Solution-Tek | NPRM & Distribution | Salil Seth | R1 | 2026-08-25 | Salil will check with Solution-tek on solution
10 | Unified Boarding Pass | Shreenivas, Subham Srivastava | PSS Integration, Airport Systems, QR Feasibility, Regulatory Approval, Design Team Capacity, Business Sign-Off | PSS, AOCS, Airport Ops, Design | Randhir, Sachin, Aditya, Shreenivas | R3 | 2026-12-31 | The details have been shared with Sachin from the PSS team for validation with Navitaire. Sachin will share further updates once he receives their feedback. |  |  |  |  | 2026-08-25
11 | Baggage Visibility, Gate & Baggage Gate & Baggage Info | Meenakshi Jain | BRS Providers, Airport APIs, Baggage Systems | Baggage Team, Airport Ops | Vinay Yadav, Randhir, Aditya Kapur | R3 | 2026-12-31 | POC required from Kshitij & PSS. PRISM is having the data, need PSS validattion on the real-time data as PRISM lags some information. Khshitij will help on the data to be reflecting on Nav Test.
12 | Automated Recovery | Lakshmi | PSS, Inventory Engine, Salesforce, Decision Engine | Digital, CX | Mayank Tyagi | R2 | 2026-11-25
13 | Hotel Voucher Automation | Lakshmi | Vernost Integration, Salesforce | CX, Digital | Mayank Tyagi | R2 | 2026-11-25
14 | AI Engine & OCC Dashboard | Lakshmi | Data Platform, Flight Feeds, AI Models, OCC Data | OCC, Data Team | Mayank Tyagi | R2 | 2026-11-25
15 | Airport API Integration | Digital/AOCS | DIAL, MIAL, BIAL APIs, Airport Agreements | AOCS, Digital | Aditya, Heena, Gaurav Malhotra | R2 | 2026-11-25
16 | BRS API Integration | Meenakshi Jain | BRS Vendors, Airport Baggage Systems | Baggage Team, Vendors | Randhir, Vinay | R3 | 2026-12-31
17 | Timeline-based journey view Phase 2 | Subham Srivastava | UX Design, PSS APIs, AOCS Inputs | CX, Design, AOCS Digital | Randhir, Vinay, Kshitij | R3 | 2026-12-31
18 | Trip Companion Explore Screen Cards | Subham Srivastava, Nihardip, Shreenivas | UX Design |  | Subham Srivastava, Nihardip, Shreenivas | R1 | 2026-08-25
Note on L4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No design changes are required at this stage. However, if any enhancement opportunities are identified during the implementation phase, we can evaluate and incorporate them accordingly.

## Sheet2
Release | EPIC | Comments as on 16Jul2026 | Comments as on 17Jul2026
R1 | Date Change Indicators | Subham & Prayas will have a meeting today to discuss on the feedback | Totally different requirement as per the discussion between Design & Product
R1 | Journey Duration Banner |  | No change or blocker. This on track.
R1 | Single Web Check-In |  | No change or blocker. This on track.
R1 | Static Airport Maps & Transfer Guidance | Map API needs to be procured by respective Airport manager for authenticity As per Vinay POC needs to be done and single airport needs to be selected. API compatibility needs to be checked. | Aditya & Vinay needs to confirm on the airport selection
R1 | Timeline Journey View P1 - Step-by-step journey, check-in, Boarding Pass |  | Dependencies are on user stories though shared today. Review is in progress. Design Team will share further their understanding.
R1 | Connection status notifications
R1 | Operations Dashboard | 1. Follow-up meeting with PRISM, Solution tek for requirements. Monday will be the day requirement will be freezed
R1 | BluChip BLU1/2/3 + Heart (Digital) and Physical
R1 | Connection Disruption Management | Salil will check with Solution-tek on solution
R3 | Unified Boarding Pass | The details have been shared with Sachin from the PSS team for validation with Navitaire. Sachin will share further updates once he receives their feedback.
R3 | Baggage Visibility, Gate & Baggage Gate & Baggage Info | POC required from Kshitij & PSS. PRISM is having the data, need PSS validattion on the real-time data as PRISM lags some information. Khshitij will help on the data to be reflecting on Nav Test.
R2 | Automated Recovery
R2 | Hotel Voucher Automation
R2 | AI Engine & OCC Dashboard
R2 | Airport API Integration
R3 | BRS API Integration
R3 | Timeline-based journey view Phase 2
R1 | Trip Companion Explore Screen Cards |  | Design team will share the feedback on the cards design done by engineering team.