PROGRAMME PLAN

Connection Enhancement Program

| Name | Connection Enhancement Program |
| --- | --- |
| Sponsors | Summi Sharma (SVP, ifly & CX) ¦ Charu Verma (Head of Business Technology (Enterprise) - Digital |
| Version | V1.1 |
| Program Start | 07-Jul-2026 |
| Author | Swati Kothiyal |
| Custodian | Sunil Kumar |
| Approver | Naresh Rao, Summi Sharma |
| Department | Digital (Web and Mobile) |

1. Program Overview	3

2. Program Objectives	3

3. Features Estimates	3

4. Workstreams	5

5. Delivery Approach	5

6. High-Level Milestones	6

7. Stakeholder Engagement	7

8. Governance	7

9. Communication Plan	8

10. Risks & Assumptions	8

11. Success Measures	9

12. Next Steps	9

# 1. Program Overview

Purpose

The Connections Enhancement Program aims to create a differentiated connecting journey experience by integrating digital capabilities, operational processes, airport services and customer communications into a seamless end-to-end product.

The program will be delivered in a phased approach, beginning with customer-facing quick wins followed by strategic capabilities that improve operational efficiency and customer satisfaction.

# 2. Program Objectives

- Deliver a differentiated connecting flight experience.

- Improve customer confidence during connecting journeys.

- Enhance digital engagement across Web and Mobile.

- Reduce customer effort through proactive communication.

- Improve operational efficiency through integrated processes.

- Increase Connecting Journey NPS.

# 3. Features Estimates

Release 1

| Feature | CX Intent | Key Dependencies | Comments | Target Go- Live Date | Platform | Design Date |
| --- | --- | --- | --- | --- | --- | --- |
| Date change indicators | Highlight when arrival/departure date changes across connecting segments. | PSS itinerary data, UX designs | Already available in the app, leveraging ETA and STA differentiation through Kafka events. | 25-Aug-26 | Web & App | 16-Jul-26 |
| Journey duration banner | Show total travel time and layover duration clearly. | Schedule/OCC/Network/PSS team | Available in the system and handled through two scenarios: Standard and Delayed cases. A separate discussion with the business is required to finalize the approach for airport transfers. | 25-Aug-26 | Web & App | 20-Jul-26 |
| Single web check-in | Allow customers to check in for full journey from one flow. | PSS/DCS rules, multi-sector check-in logic | The current system already supports this capability. For multi-sector check-in scenarios, the DROID service will be invoked to process the transaction. | 25-Aug-26 | Web & App | No design changes are currently required. However, if an enhancement is identified during implementation, we can proceed accordingly. 21jul26 |
| Static airport maps | Provide simple transfer maps for DEL/BOM etc. | Airport layout inputs, content ownership | Details to be shared by the PSS team. Airport APIs need to be reviewed and validated. | 25-Aug-26 | App Only | 22-Jul-26 |
| Timeline-based journey view - Phase 1 | Step-by-step journey, check-in, boarding, Gate, except Bag journey | UX, PSS, AOCS | Available in the current solution. The Trip Companion feature is supported in the new design through the API service. | 25-Aug-26 | App Only | POC required from Kshitij & PSS. 17-jul-26 24-Jul-26 Design |
| Connection status notifications | On Track / At Risk / Missed alerts. | NetOps feed, risk rules, notification engine | Available in the current solution. The Trip Companion feature is supported in the new design of app; notification support requires further validation. | 25-Aug-26 | App Only | Need to discuss with Lakshmi and Mayank |
| Operations Dashboard | Provide centralized operational monitoring and decision support | Operational data sources, OCC, flight and airport feeds | This is with PRISM team | 25-Aug-26 |  | Need to discuss with Lakshmi and Mayank |
| BluChip BLU1/2/3 + Heart (Digital) and Physical | Surface loyalty status and priority treatment. | Loyalty/CRM tagging, UI rules/Capilary/CIAM | Available in LMS; pending validation with the CX and Loyalty teams. | 25-Aug-26 | Web & App | Digital: (31-Jul-26) |
| Connection Disruption Management | The end-to-end disruption handling experience will require integration with the Solution Tech platform to enable: - Alternate Flight Recommendations - Hotel Suggestions - Passenger Protection Journey - Missed Connection Recovery Flows | Digital/Solution-Tek |  | 25-Aug-26 | App Only | Solution Tech Team (Salil / Amar team) to be onboarded |

Release 2

| Feature | CX Intent | Key Dependencies | Comments | Target Go- Live Date | Platform | Design Date |
| --- | --- | --- | --- | --- | --- | --- |
| Airport API Integration | Enable real-time data exchange between airline and airport systems | Digital, AOCS PSS integration | This capability should be implemented across all airports to ensure consistent customer experience. A partial rollout may lead to inconsistent user experience and will require approval from both the CX and AOCS teams. | 25-Nov-26 | App Only |  |
| AI-powered Connection Monitoring | Proactively identify and manage at-risk passenger connections | Flight status feeds, passenger itinerary data, AI models | This capability should be implemented across all airports to ensure consistent customer experience. A partial rollout may lead to inconsistent user experience and will require approval from both the CX and AOCS teams. | 25-Nov-26 | Web & App |  |
| Automated Recovery | Automate recovery actions during disruptions and missed connections | Inventory availability, CRM, communication platform, decision engine |  | 25-Nov-26 | Web & App |  |

Release 3

| Feature | CX Intent | Key Dependencies | Comments | Target Go- Live Date | Platform | Design date |
| --- | --- | --- | --- | --- | --- | --- |
| Timeline-based journey view Phase 2 | Bag drop, security, connection, belt. | Airport APIs, DCS/BRS feed | As discussed with AOCS Digital (Randhir), IndiGo uses its own BRS at select airports and the airport's BRS at others, the integration model is currently being evaluated. Any phased or partial rollout will require approval from both the CX and AOCS teams. | 31-Dec-26 | App |  |
| Gate and baggage belt info | Push gate and belt updates in app/WhatsApp. | Airport APIs, DCS/BRS feed | Same as above | 31-Dec-26 | App |  |
| Live Baggage Tracking | Provide real-time baggage status visibility to passengers | Baggage systems, airport handlers, airport APIs, notifications | Same as above | 31-Dec-26 | App |  |
| Unified Boarding Pass | Provide a seamless and consistent boarding experience across all touchpoints | PSS integration, airport systems, boarding pass standards, digital channels | This initiative requires senior management approvals, including approval from Mr. Rahul Bhatia. The CX Business team will initiate the approval process. | 31-Dec-26 | Web & App |  |

Out of Scope

- Core reservation system replacement

- Airport infrastructure changes

- Third-party commercial agreements

- Non-connecting passenger enhancements

# 4. Workstreams

| Workstream | Scope |
| --- | --- |
| Customer Experience | Journey design and customer requirements |
| Digital Platforms | Website and Mobile enhancements |
| Airport Operations | Airport processes and transfer experience |
| Technology | System integrations and APIs |
| CRM & Communications | Notifications and customer messaging |
| Program Management | Governance, planning and reporting |

# 5. Delivery Approach

| Phase 1 – Quick Wins (0–3 Months) | Phase 2 – Strategic Enhancements (3–6 Months) |
| --- | --- |
| - Journey Timeline - Date Change Indicator - Journey Duration - Single Web Check-in - Re-Designing of Boarding Pass - Airport Maps - Connection Notifications - Gate & Belt Information - BluChip Classification | - Unified Boarding Pass - Live Baggage Tracking - Airport API Integration - AI-powered Connection Monitoring - Automated Recovery - Operations Dashboard |

# 6. High-Level Milestones

| Milestone | Target | Start Date | End Date |
| --- | --- | --- | --- |
| Program Kick-off | Week 1 | 29-Jun-2026 | 03-Jul-2026 |
| SPOC Confirmation | Week 1 | 01-Jul-2026 | 10-Jul-2026 |
| Requirement Workshops Design | Weeks 2–3 | 07-Jul-2026 | 10-Jul-2026 |
| Solution Finalization | Week 4 | 20-Jul-2026 | 24-Jul-2026 |
| Development Commencement | Month 2 |  |  |
| UAT | Month 3 | 03-Aug-2026 | 12-Aug-2026 |
| Release 1 Go-Live | End of Month 3 |  |  |
| Release 2 Planning | Month 3 |  |  |
| Release 2 Go-Live | End of Month 6 |  |  |

# 7. Stakeholder Engagement

| Stakeholder | SPOC Name | Responsibility | Accountability | Consulted | Informed |
| --- | --- | --- | --- | --- | --- |
| Customer Experience | Aiswary.Gupta@goIndiGo.in Melvin.Oommen@goIndiGo.in Heena.Malhotra@goIndiGo.in | Program Sponsor | Overall program success, business outcomes, budget approval, final business sign-off | Digital, AOCS, Marketing, PRM | Leadership Team |
| Digital | Swati.kothiyal@goindigo.in Rajat.x.upreti@goindigo.in Abhishek.malhotra@goindigo.in (IndiGo Access-B2B) | Product, Delivery, Design | Digital solution delivery, requirements management, release planning, implementation | Customer Experience, PSS, Design Team, AOCS, PRM | Leadership Team |
| PSS | Sachin.Kumar12@goIndiGo.in | Reservation and Check-in integration | PSS integration delivery, system configuration, technical sign-off | Digital, AOCS, Customer Experience, PRM | Leadership Team |
| Airport Operations (AOCS) | (Digital) Kshitij.Khshtarpal1@goIndiGo.in Randhir.Chambail1@goIndiGo.in MOHIT.GOYAL2@goIndiGo.in | Airport experience | Operational readiness, process compliance, airport implementation | Customer Experience, Digital, PSS, PRM | Leadership Team |
| Marketing | Jonty.1@goIndiGo.in | Customer communication | Customer-facing communication strategy, campaign execution, content approvals | Customer Experience, Digital, AOCS, PRM | Leadership Team |
| PRM, RMConfig | Shubham.Thakur@goIndiGo.in | Business prioritization | Business prioritization, commercial alignment, business approvals | Customer Experience, Digital, AOCS, PRM | Leadership Team |
| External Partners |  | API and operational integrations | Delivery of third-party integrations, API readiness, partner-side testing | Digital, PSS | Leadership Team |
| Design Team | SHREENIVAS.RANSUBHE@goIndiGo.in | Designs for requirement | UX/UI design delivery, design consistency, usability validation | Digital, Customer Experience, AOCS, PRM | Leadership Team |
| Ancillary Team | Shubham.Gupta9@goIndiGo.in | Add-on products and services offered. |  | Digital, Customer Experience, AOCS, PRM, Ancillary | Leadership Team |

# 8. Governance

Executive Steering Committee

- Strategic direction

- Priority decisions

- Business approvals

Program Management Office

- Overall program management

- Milestone tracking

- Risk and issue management

- Executive reporting

Workstream Leads

- Requirement finalization

- Solution design

- Delivery management

- UAT coordination

# 9. Communication Plan

| Audience | Frequency | Purpose |
| --- | --- | --- |
| Steering Committee | Fortnightly | Strategic review |
| Program Team | Weekly | Progress review |
| Workstream Leads | Weekly | Dependency management |
| Project SPOCs | Weekly | Status and actions |
| Leadership | Monthly | Executive dashboard |

# 10. Risks & Assumptions

| Risk | Mitigation |
| --- | --- |
| Cross-functional dependencies | Weekly governance reviews |
| Integration delays | Early technical assessment |
| Resource availability | Capacity planning |
| External dependencies | Early engagement with airport and technology partners |

# 11. Success Measures

| KPI | Target Outcome |
| --- | --- |
| Connecting Journey NPS | Improvement over baseline |
| App Engagement | Increased usage |
| Customer Contacts | Reduced support requests |
| Feature Adoption | High customer utilization |
| On-time Delivery | Milestones achieved as planned |

# 12. Next Steps

- Nominate SPOCs from all participating functions.

- Confirm Phase 1 scope and priorities.

- Complete requirement workshops.

- Finalize solution design and dependencies.

- Publish the integrated delivery plan.

- Initiate development for Quick Wins.

- Establish the governance cadence and reporting framework.