Connecting Flight Experience Transformation

Program Objective

Deliver an App-first, anxiety-free connecting flight experience by improving visibility, reducing passenger uncertainty, and enabling proactive recovery to enhance NPS and operational efficiency.

Program Strategy

| Principle | Description |
| --- | --- |
| Integrated Program | Single program vs siloed initiatives |
| App-First | Customer communication driven via mobile |
| Proactive Experience | Predict + Notify + Resolve |
| Phased Delivery | Quick Wins → Advanced AI-led capabilities |

Workstream-Based Execution Plan

Customer Experience (CX) Enhancements

| Capability | Key Deliverables | Owner |
| --- | --- | --- |
| Journey Display | Date change indicator, total duration, layover visibility | Sunil / Subham |
| Timeline View | Step-by-step journey experience | Sunil / Subham |
| Connection Tags | Short/Long connection improvements | Subham / Randhir |
| First Port of Entry | Intl baggage instructions | Sunil / Subham |

Airport & Navigation Experience

| Capability | Key Deliverables | Owner |
| --- | --- | --- |
| Terminal Guidance | Transfer/shuttle guidance | Digital / Sunil |
| Airport Maps | Static maps + transfer points | Sunil / Subham |
| Airport API Integration | DIAL/MIAL/BIAL | Subham |

Check-in & Boarding Experience

| Capability | Key Deliverables | Owner |
| --- | --- | --- |
| Web Check-in | Single-click journey check-in | Sunil |
| Single Boarding Pass | Unified boarding pass (dynamic QR feasibility) | Randhir / Arvind / Subham |
| Boarding Pass Modernization | Standardized design across channels | Sunil / Subham |

Baggage Visibility & Handling

| Capability | Key Deliverables | Owner |
| --- | --- | --- |
| Baggage Tracking | End-to-end journey view | Meenakshi / Sunil / Subham |
| Baggage APIs | Integration with BRS & airport systems | Randhir / Subham |

Proactive Communication & Alerts

| Capability | Key Deliverables | Owner |
| --- | --- | --- |
| Connection Alerts | On Track / At Risk / Missed | Subham |
| Gate/Belt Notifications | Real-time updates in app | Lakshmi / Subham / Heena |
| App Campaign | App-first behavioral shift | Raja / Heena |

Recovery & Operations Automation

| Capability | Key Deliverables | Owner |
| --- | --- | --- |
| Auto-Recovery | Alternate flights, refunds, hotel options | Lakshmi |
| OCC Dashboard | Monitoring misses, baggage issues, risks | Lakshmi |
| AI Decision Engine | Recommendation engine | Lakshmi |

Phase-wise Delivery Plan

Phase 1: Quick Wins (0–3 Months)

| Feature | Outcome |
| --- | --- |
| Date Change Indicators | Reduced confusion |
| Journey Duration Banner | Better journey clarity |
| Single Web Check-in | Seamless onboarding |
| Static Airport Maps | Basic navigation |
| Timeline View | Guided experience |
| Connection Notifications | Risk awareness |
| Gate & Belt Info | Real-time awareness |
| BluChip Tagging | Tiered experience clarity |

Phase 2: Advanced Capabilities (3–6 Months)

| Feature | Outcome |
| --- | --- |
| Unified Boarding Pass | Simplified journey |
| Baggage Tracking | Full transparency |
| Auto-Rebooking | Reduced disruption stress |
| Hotel/Voucher Integration | Faster recovery |
| AI Decision Engine | Predictive experience |
| OCC Dashboard | Operational control |
| Paperless Boarding | Digital-first adoption |

Technical Dependency Map

| Dependency | Impact Area | Criticality |
| --- | --- | --- |
| Airport Map APIs (DIAL/MIAL/BIAL) | Navigation UX | High |
| Gate/Baggage APIs | Real-time visibility | High |
| BRS Integration | Baggage tracking | High |
| Dynamic QR | Boarding pass | Medium-High |
| SolutionTek + Salesforce | Recovery flows | High |
| AI Engine | Decision automation | High |
| UI/UX Designs | Frontend Presentation Layer | High |

Milestone Plan (Indicative)

| Milestone | Timeline | Owner |
| --- | --- | --- |
| Program Kick-off & Alignment | Week 1 | Swati / Raja |
| Feature Breakdown & JIRA Planning | Week 2–3 | Swati |
| Phase 1 Development Start | Week 3 | All Streams |
| Phase 1 Go-Live | Month 3 | Digital |
| Phase 2 Design & Architecture | Month 2–4 | Lakshmi / Arch Team |
| Phase 2 Execution | Month 4–6 | All Streams |
| Full Program Rollout | Month 6 | Leadership |

Governance Model

Cadence

- Weekly Program Review → Swati / Raja

- Dependency Review (Airports/BRS/Digital) → Lakshmi / Sunil / Subham

- Steering Committee → Monthly (Leadership)

Governance Structure

| Level | Purpose |
| --- | --- |
| Program Board | Strategic decisions, prioritization |
| Working Group | Feature execution tracking |
| Tech Council | API / Integration decisions |

Key Governance Actions

- Break all features into JIRA Epics → Stories → Tasks

- Map dependencies + critical path

- Track via RAG dashboard

- Monitor:

  - % Phase completion

  - API readiness

  - Release slippages

Success Metrics (KPIs)

| KPI | Measure |
| --- | --- |
| NPS Improvement | +X% (Connecting passengers) |
| Missed Connections | Reduction % |
| App Adoption | % increase |
| Customer Queries | Reduction in support tickets |
| Baggage Visibility | % tracked journeys |
| Auto-Recovery Usage | % automated cases |

Risks & Mitigation

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Airport API delays | Feature blocks | Early engagement & fallback (static maps) |
| BRS integration gaps | Incomplete baggage view | Parallel API evaluation |
| Dynamic QR feasibility | Boarding delay | Hybrid rollout |
| Cross-team dependency | Delivery delay | Weekly governance tracking |

Program Summary

Integrated, app-first transformation
 Immediate quick wins (Phase 1) to reduce anxiety
 Advanced AI-led experience (Phase 2)
 Strong governance with clear ownership
 Dependency-driven execution

Next Steps (Action-Oriented)

- Convert all actions → JIRA Epics (by workstream)

- Create Integrated Delivery Plan (IMP) with dependencies

- Launch Weekly Governance Dashboard (RAG-based)

- Lock Phase 1 scope and timelines (within 1 week)