## Sheet1
*** Please note that the timelines mentioned are hypothetical estimates at this stage. Definitive timelines will be shared after evaluating the discussed points and coordinating with the respective stakeholders.
Area | CX Understanding | Why It Matters
Program Objective | Build an app-first, anxiety-free connecting-flight experience. | Connections are high-stress journeys; poor visibility increases contact centre calls and NPS impact.
Current Problem | Customer does not get one consolidated view of connection status, journey steps, gate/belt, baggage, terminal movement and recovery options. | Passenger depends on airport staff/contact centre instead of self-service.
Product Direction | Move from “flight information display” to “journey orchestration”. | CX should own end-to-end journey clarity, not only individual features.
Delivery Approach | Phase 1 quick wins: Jul–Sep 2026. Phase 2 scale/differentiation: Oct 2026–Mar 2027. | Helps separate immediately deliverable UI/data improvements from complex airport/API/AI integrations.
Governance | CX + Digital + OCC + Loyalty + Airport Ops + PSS + external partners. | This cannot be managed as only a Digital project. CX must drive business priority and adoption.
Features Estimates
Feature | CX Intent | Execution Complexity | Logical Timeline | Key Dependencies | Available from System | Platform
Date change indicators | Highlight when arrival/departure date changes across connecting segments. | Low | 4–6 weeks | PSS itinerary data, UX designs | Yes
Journey duration banner | Show total travel time and layover duration clearly. | Low | 4–5 weeks | Schedule/OCC/Network/PSS team | Yes - Need airport transfers to be discussed
Single web check-in | Allow customer to check in for full journey from one flow. | High | 8–12 weeks | PSS/DCS rules, multi-sector check-in logic | Yes, however not available for NORSE ( LKO-AMS)
Static airport maps | Provide simple transfer maps for DEL/BOM etc. | Medium | 5–7 weeks | Airport layout inputs, content ownership | PSS twam will share the details, Need Airport APIs to be checked
Timeline-based journey view | Step-by-step journey: check-in, bag drop, security, boarding, connection, belt. | Medium | 8–10 weeks | UX, PSS, gate/belt feed/AOCS | Yes - Trip companion is available in the new design - API service
Connection status notifications | On Track / At Risk / Missed alerts. | High | 10–14 weeks | NetOps feed, risk rules, notification engine | Yes - Trip companion is available in the new design - for notifications we need to check
Gate and baggage belt info | Push gate and belt updates in app/WhatsApp. | High | 10–16 weeks | Airport APIs, DCS/BRS feed | We need to check on the API service if possible
BluChip BLU1/2/3 + Heart | Surface loyalty status and priority treatment. | Medium | 5–8 weeks | Loyalty/CRM tagging, UI rules/Capilary/CIAM | Service is available - LMS) - Need to be checked with CX & Loyalty team
Execution Plan
Phase | Duration | Scope | Output
Discovery & CX Alignment | 2 weeks | Confirm customer pain points, journey map, CX priority, KPIs, pilot airport. | Signed CX scope and success metrics
Design & Data Validation | 3–4 weeks | UX flows, copy, data source confirmation, API feasibility. | Wireframes, data contracts, dependency tracker
Phase 1 Build | 8–10 weeks | Date indicator, duration banner, static maps, timeline view, BluChip surfacing. | Pilot-ready app/web experience
Phase 1 Pilot | 3–4 weeks | DEL / DEL-BOM controlled rollout. | NPS/contact-centre/adoption validation
Phase 2 Build | 16–20 weeks | Single check-in, risk engine, gate/belt, dynamic maps, baggage visibility. | Scalable operational capability
Scale & BAU Handover | 4 weeks | SOPs, dashboards, support model, training. | Operationalized CX product
Resource Estimate
Role | Count | Duration | Responsibility
CX Product Owner | 1 | Full program | Own customer journey, prioritization, CX sign-off
Program Manager / PMO | 1 | Full program | Plan, RAID, governance, milestone tracking
Business Analyst | 1–2 | 3–6 months | BRD, journey rules, acceptance criteria
UX Designer | 1 | 2–3 months | Journey screens, notification copy, maps, timeline
Mobile Developers | 2–3 | 3–6 months | iOS/Android changes
Web Developers | 1–2 | 3–4 months | Web check-in/journey display
Backend/API Developers | 2–3 | 4–6 months | PSS, NetOps, airport, BRS integrations
QA Team | 2–3 | Full build cycles | Functional, regression, journey testing
Data/Analytics Resource | 1 | Full program | KPI/NPS dashboards, GA4 instrumentation
OCC/Airport Ops SME | 1–2 part-time | Full program | Operational rules, gate/belt, misconnect logic
Loyalty SME | 1 part-time | 1–2 months | BluChip logic and validation
Key Risks
Risk | CX Action Required
Features become fragmented | Position this as one integrated connections journey program.
API delays from airports/BRS | Escalate early; create static/manual fallback for Phase 1.
Overloaded customer UI | Use progressive disclosure; show only next-best action.
Incorrect “At Risk” alerts | Start with rule-based pilot and human/OCC validation.
Low adoption | CX must drive app-first communication, airport nudges and contact-centre scripts.
SLA/compliance | Vendor support and service obligations should be tracked; the attached SLA allows service credits and termination rights in case of repeated SLA failure.
objective is not to deliver isolated features; we need to own the complete connecting passenger journey. Phase 1 should give immediate visibility and confidence to the customer. Phase 2 should make the journey intelligent through risk prediction, baggage visibility, gate/belt integration and automated recovery. CX will own the customer problem, Digital will own execution, and OCC/Airport Ops will own operational accuracy.”