## Cover
Connections Enhancement Program – Program Plan v1.0
Anchored on an app-first, anxiety-free connecting flight experience
Sponsors | Summi Sharma (SVP, ifly & CX) ¦ Charu Verma (Head of Business Technology (Enterprise) - Digital
Program Lead (Business) | Raja Karmakar – Director, Customer Experience
Program Lead (PMO) | Swati Kothiyal – Digital PMO
Program Start | 01-Jul-2026
Phase 1 (Quick Wins) End | 30-Sep-2026
Phase 2 (Scale & Differentiate) End | 31-Mar-2027
Program Closure | 30-Apr-2027
Document Date | 25-Jun-2026
Version | 1.0 (Initial Baseline)
Distribution | EXCO, Steering Committee, Workstream Leads
Document Owner | Raja Karmakar (CX) / Swati Kothiyal (PMO)
Objective
Assess readiness for a differentiated connecting flight product and define customer experience enhancements to reduce passenger anxiety and improve NPS.
Guiding Principle
Build this as ONE integrated program, not as separate initiatives – anchored on an app-first, anxiety-free connecting experience.
Overall Direction
Build an app-first, anxiety-free connecting flight experience with proactive communication, baggage visibility, automated recovery, and AI-enabled connection management, while delivering quick wins immediately and progressively evolving toward a world-class hub-and-spoke customer experience.
Workbook Contents
Sheet | Description
Cover | Program overview, sponsors, objective, contents
Doc_Control | Version history, distribution list, references
Executive_Summary | Leadership snapshot of the program
Business_Case | Why now, voice of customer, strategic alignment, business case
Vision_Principles | Vision, mission and 7 guiding principles
Objectives_KPIs | Program objectives and success metrics
Scope | In scope, out of scope, geographical scope
Stakeholders | Customer segments, internal stakeholders, partners
Roadmap | Delivery approach, phased roadmap, key milestones
Phase1_Quick_Wins | Granular Phase 1 plan – 54 tasks
Phase2_Scale_Differentiate | Granular Phase 2 plan – 49 tasks
Gantt_Phase1 | Weekly Gantt – Phase 1 (Jul–Sep 2026)
Gantt_Phase2 | Weekly Gantt – Phase 2 (Oct 2026 – Mar 2027)
Gantt_Overall | Monthly program Gantt (Jul 2026 – Apr 2027)
Tech_Dependencies | Architecture, dependencies, data flows, NFRs
RACI | 21 action items × 17 stakeholders
Governance | 3-tier governance, forums, escalation, decision authority
RAID_Log | Risks, assumptions, issues, dependencies – 36 entries
Resource_Plan | Core team and effort estimate
Budget | Indicative budget and funding status
Comms_Plan | Internal/external communication and adoption levers
Quality_Compliance | Quality gates, compliance, audit trail
KPI_Dashboard | Measurement approach, dashboards, benefits timeline
Reporting | Reporting artefacts and cadence
Closure_Criteria | Program closure criteria
Glossary | Terms and definitions
Sign_off | Sign-off block for sponsors and leads

## Doc_Control
Document Control
Version History
Version | Date | Author | Reviewer | Approver | Changes
1.0 | 25-Jun-2026 | Raja Karmakar | Naresh Rao | Summi Sharma & Charu Verma | Initial baseline post Connections Enhancement Catch-up dated 23-Jun-2026
Distribution List
Name | Role | Department
Summi Sharma | Sponsor – SVP | ifly & CX
Charu Verma | Sponsor – SVP | Digital
Naresh Rao | Reviewer – VP | Customer Experience
Raja Karmakar | Program Lead (Business) | Customer Experience
Swati Kothiyal | Program Lead (PMO) | Digital
Sunil Kumar | Workstream Lead – App/Web | Digital
Subham Srivastava | Workstream Lead – Platform | Digital
Lakshmi Gopalakrishnan | Workstream Lead – AI/OCC/Recovery | Digital
Randhir Chambail | Workstream Lead – Boarding Pass | Digital
Meenakshi Jain | Workstream Lead – Baggage | Digital
Heena Malhotra | Workstream Lead – CX Content | Customer Experience
Vinay Yadav | Workstream Member – Airport Systems | Digital
Nihardip Sharma | Workstream Member – Contingency | Digital
Jochen Hoesch | Workstream Member – Data/AI Platform | Digital
Isha Gandhi | Workstream Member – CX Ops | Customer Experience
Mahak Batra | Workstream Member – CX Ops | Customer Experience
Reference Documents
• Meeting Minutes – Connecting Flight Product (23-Jun-2026)
• Customer NPS Insights – Connecting Journeys (Q1–Q2 FY27)
• DGCA Guidelines on Customer Communication & Boarding
• IATA BCBP Standard Reference (for unified boarding pass)
• IndiGo CX Strategy Deck FY27
• Connections_Enhancement_Program_Plan_v1.0.docx (companion Word document)

## Executive_Summary
1. Executive Summary
IndiGo is launching the Connections Enhancement Program to transform the connecting flight experience for customers across our domestic and international network. As we scale our hub-and-spoke model and expand international codeshare and self-connect routes, the connecting journey has emerged as a high-anxiety, high-impact moment that directly influences NPS, repeat purchase, and brand affinity. This program is being delivered as ONE integrated, app-first initiative – not as a set of disconnected digital features.
Co-sponsored by Summi Sharma (SVP, ifly & CX) and Charu Verma (SVP, Digital), the program brings together Customer Experience, Digital, Network Operations, Loyalty, Legal and external airport & technology partners. It is structured in two phases – Quick Wins (Jul–Sep 2026) and Scale & Differentiate (Oct 2026 – Mar 2027) – followed by a Benefits Realization review in Apr 2027.
Phase 1 delivers 11 customer-visible quick wins across the journey display, web check-in, airport maps, timeline view, connection risk alerts, gate/belt notifications, BluChip loyalty surfacing, terminal guidance, first-port-of-entry guidance and a unifying prototype. Phase 2 delivers 10 transformational capabilities including unified digital boarding pass with dynamic QR, end-to-end baggage visibility, auto-recovery (rebooking, refund, hotel & voucher), AI-driven connection management with an OCC decision engine, paperless boarding adoption campaign and dynamic airport map APIs.
The program targets a measurable improvement in connecting-journey NPS (+12 points), a reduction in inbound contact-centre volumes related to connections (-25%), an increase in app-first self-serve adoption for recovery (+40%) and a reduction in disrupted-passenger handling cost per misconnect (-20%). This document is the baseline plan governing scope, schedule, governance, risk and quality across both phases.

## Business_Case
2. Program Context & Business Case
2.1 Why Now
IndiGo's network is expanding rapidly with deeper hub operations at DEL and BOM, growing international point-to-point and codeshare routes, and a rising share of self-connect bookings. Customer expectations are simultaneously shifting toward proactive, app-first experiences, benchmarked against global carriers such as KLM (Sentry), Delta (proactive recovery), Emirates (digital BP) and Air India (Fly Prior). Regulatory direction from DGCA continues to evolve around customer communication during disruption, making proactive, audit-safe communication a strategic must-have. The current connecting experience is fragmented – sector-wise check-in, no unified boarding pass, limited baggage visibility post check-in, and manual recovery during misconnects – which directly hurts NPS and increases cost-to-serve.
2.2 Voice of Customer
Customer interviews, contact-centre logs, social listening, and post-flight NPS surveys repeatedly surface the following themes for connecting journeys:
• "I don't know if I will make my connection."
• "I have to check in twice for the same booking."
• "I don't know where my bag is after the first leg."
• "When the connection is missed, I have to call the contact centre or stand in queue."
• "I don't know which terminal or gate to go to – signage and apps disagree."
2.3 Strategic Alignment
This program aligns directly with three top-level strategies: (a) the IndiGo CX Strategy of an app-first, anxiety-free experience that delivers world-class hub-and-spoke service; (b) the Digital roadmap to evolve the IndiGo app into a connected super-app for travel; and (c) the ifly transformation agenda to industrialise core CX moments. It also de-risks our codeshare and international expansion by establishing a single product foundation that can be replicated across partners and hubs.
2.4 Business Case Summary
The indicative business case is summarised below; detailed financials are tracked in a companion business case sheet maintained by Finance & PMO.
Lever | Target | Annualised Impact (Indicative)
Connecting-journey NPS | +12 pts | Repeat purchase uplift; stronger brand affinity
Contact-centre call deflection (connections) | -25% | INR savings in handling cost
App-first recovery adoption | +40% | Lower at-airport queue cost
Misconnect handling cost | -20% per misconnect | INR savings on hotel + rebooking
Codeshare readiness | Day-1 capability | Faster time-to-market for new partners

## Vision_Principles
3. Vision, Mission & Guiding Principles
3.1 Vision
"Make every IndiGo connecting journey anxiety-free, app-first, and world-class – so that customers feel in control before, during and after disruption."
3.2 Mission
To deliver an integrated connecting flight product that combines proactive communication, baggage visibility, automated recovery, AI-enabled connection management, and a paperless boarding journey – built once and scaled across all hubs.
3.3 Guiding Principles
1. One integrated program, not separate initiatives.
2. App-first by default; airport touchpoints as backup.
3. Proactive communication over reactive recovery.
4. Visibility before automation – never automate what we cannot show.
5. Customer-centric language; audit-safe and regulator-compliant content.
6. Build → Pilot → Scale; never big-bang.
7. Measure NPS and operational KPIs from Day 1.

## Objectives_KPIs
4. Objectives & Success Metrics
4.1 Program Objectives
1. Reduce customer anxiety in the connecting journey through proactive, app-first communication.
2. Enable single-PNR experiences (single check-in, single boarding pass, single recovery flow).
3. Provide end-to-end visibility of journey, baggage, and disruption recovery.
4. Establish a proactive AI-based decision engine for connection risk and recovery management.
5. Drive paperless boarding adoption and digital-first behaviour at scale.
6. Build a scalable, codeshare-ready foundation for international hub growth.
4.2 Success Metrics (Outcome KPIs)
KPI | Baseline (FY27 H1) | Phase 1 Target (Sep'26) | Phase 2 Target (Mar'27) | Owner
Connecting-journey NPS | TBD | +5 pts | +12 pts | CX (Raja)
Repeat connection bookings | TBD | +3% | +8% | CX (Raja)
App-first recovery adoption | TBD | 15% | 40% | CX + Digital
Calls per misconnect (contact centre) | TBD | -10% | -25% | Contact Centre
Bag-related complaints (connecting) | TBD | -5% | -20% | Airport Ops
At-airport queue length (recovery) | TBD | -10% | -30% | Airport Ops
Paperless boarding adoption | TBD | 25% | 50% | Digital + CX
4.3 Leading Indicators (Operational KPIs)
• Airport API uptime ≥ 99% per hub.
• Push notification deliverability ≥ 95% across iOS/Android.
• AI model precision/recall ≥ agreed threshold (shadow mode → live).
• Contact-centre AHT for connection queries reducing month-on-month.
• Recovery SLA: rebooking < 5 min, hotel allocation < 30 min from disruption decision.
• App engagement on connection screens (DAU/MAU) trending up week-on-week.

## Scope
5. Scope
5.1 In Scope
• Date change indicators in itinerary
• Total journey duration & layover banner
• Single-click web check-in across the entire journey
• Static (Phase 1) and dynamic (Phase 2) airport maps with transfer points
• Step-by-step journey timeline
• Connection risk alerts (On Track / At Risk / Missed)
• Gate and baggage belt notifications in app
• BluChip tier surfacing across touchpoints
• Terminal-to-terminal transfer & shuttle guidance
• First port of entry baggage guidance for international arrivals
• Unified UI prototype across all Phase 1 use cases
• Unified digital boarding pass with dynamic QR
• Boarding pass modernization & standardization across app, web, email, PDF
• End-to-end baggage visibility (BRS integration)
• Auto-rebooking & refund automation
• Hotel & voucher integration (Vernost + Salesforce)
• AI decision engine & OCC dashboard
• Paperless boarding adoption campaign
• Short/long connection tag modernization
• Airport map APIs – DIAL/MIAL/BIAL integration
• Baggage APIs from BRS providers
5.2 Out of Scope
• Lounge access entitlement engine (handled by Loyalty roadmap)
• Inflight Wi-Fi / IFE upgrades
• Pricing and dynamic re-pricing
• Cross-airline interlining beyond existing codeshare arrangements
• Aircraft on-ground (AOG) maintenance recovery workflows
5.3 Geographical Scope
Phase 1 will pilot at DEL and on the DEL–BOM hub-and-spoke flow. Phase 2 will scale across BOM, BLR, HYD, CCU, and MAA; and progressively roll out at international hubs (IST, DOH, AUH) where IndiGo operates wide-body or codeshare connections. The international rollout sequence will be governed by airport-API readiness and regulatory approvals.

## Stakeholders
6. Customer & Stakeholder Map
6.1 Customer Segments
• Leisure travellers on multi-leg domestic/international journeys
• Business travellers prioritising tight connections
• Family travellers with assisted-travel needs
• International transit passengers (intl-to-domestic and intl-to-intl)
• Codeshare-inbound passengers
• First-time IndiGo travellers (acquisition cohort)
• BluChip members (BLU1 / BLU2 / BLU3 + Heart)
6.2 Internal Stakeholders
Group | Role | Engagement
Sponsors | Summi Sharma, Charu Verma | Strategic direction & investment decisions
Program Leads | Raja Karmakar, Swati Kothiyal | Day-to-day program leadership
Workstream Leads | Sunil, Subham, Lakshmi, Randhir, Meenakshi, Heena | Delivery accountability
Reviewers | Naresh Rao, Pratik Arjun Sen, Jochen Hoesch | Technical & CX review
Operations | OCC, Airport Ops, Contact Centre | BAU operate & feedback loop
Partners | DIAL/MIAL/BIAL/HYD/CCU airports, Vernost, BRS providers, WhatsApp BSP | Integration & external delivery
Regulatory | DGCA, IATA | Compliance & standards
6.3 External Partners
External partner engagement will be led by the respective workstream owners with PMO coordination. All commercial contracts shall be routed through Procurement and Legal. A dedicated fortnightly Airport API Sync (Subham Srivastava) and a separate Vernost integration track (Lakshmi Gopalakrishnan) will manage external delivery milestones.

## Roadmap
7. Program Approach & Phased Roadmap
7.1 Delivery Approach
The program follows an iterative, agile delivery approach with weekly sprints in Digital, a fortnightly review cadence with CX, and a monthly Steering forum chaired by sponsors. Each capability is delivered through a Design → Build → Pilot → Scale cycle. All customer-facing changes are instrumented with analytics and NPS hooks from Day 1 to enable evidence-based iteration. Pilots are scoped narrowly (DEL or DEL-BOM) and scaled only after pre-agreed success criteria are met.
7.2 Phased Roadmap
Phase 1 – Quick Wins (Jul–Sep 2026)
• Date Change Indicators
• Total Journey Duration & Layover Banner
• Single-Click Web Check-in
• Static Airport Maps with Transfer Points
• Step-by-Step Journey Timeline
• Connection Risk Alerts (On Track / At Risk / Missed)
• Gate & Baggage Belt Notifications
• BluChip Tier Surfacing (BLU1/BLU2/BLU3 + Heart)
• Terminal-to-Terminal Transfer & Shuttle Info
• First Port of Entry Baggage Guidance
• Unified UI Prototype across all Phase 1 use cases
Phase 2 – Scale & Differentiate (Oct 2026 – Mar 2027)
• Unified Digital Boarding Pass with Dynamic QR
• Boarding Pass Modernization & Standardization
• End-to-End Baggage Visibility
• Auto-Recovery – Rebooking & Refund Automation
• Hotel & Voucher Integration (Vernost + Salesforce)
• AI Decision Engine & OCC Dashboard
• Paperless Boarding Adoption Campaign
• Short / Long Connection Tag Modernization
• Airport Map APIs – DIAL/MIAL/BIAL Live Maps
• Baggage APIs from BRS Providers
Phase 3 – Benefits Realization (Apr 2027)
Post-launch NPS measurement, course corrections, scale to additional hubs (CCU, MAA, intl), and formal hand-over to BAU operations. Sponsor sign-off on benefits realization closes the program.
7.3 Key Milestones
# | Milestone | Phase | Target Date | Owner | Status | Dependencies
1 | Program Kick-off | Phase 1 | 01-Jul-2026 | Raja Karmakar / Swati Kothiyal | Not Started | Stakeholder alignment
2 | Prototype Sign-off | Phase 1 | 31-Jul-2026 | Sunil Kumar / Subham Srivastava | Not Started | UX research
3 | BluChip + Date Change Indicators GA | Phase 1 | 15-Aug-2026 | Sunil Kumar | Not Started | UI dev complete
4 | Connection Risk Alerts Pilot (DEL-BOM) | Phase 1 | 31-Aug-2026 | Subham Srivastava | Not Started | NetOps feed; WA API
5 | Quick Wins Pilot Bundle | Phase 1 | 31-Aug-2026 | Swati Kothiyal | Not Started | Multiple Phase 1 epics
6 | Phase 1 GA – All Quick Wins | Phase 1 | 30-Sep-2026 | Swati Kothiyal / Raja Karmakar | Not Started | Pilot sign-off
7 | Phase 2 Kick-off | Phase 2 | 01-Oct-2026 | Raja Karmakar / Swati Kothiyal | Not Started | Phase 1 closure
8 | Unified Boarding Pass Pilot (DEL) | Phase 2 | 31-Dec-2026 | Randhir Chambail | Not Started | Dynamic QR; airport readiness
9 | Hotel & Voucher Auto Integration GA | Phase 2 | 31-Dec-2026 | Lakshmi Gopalakrishnan | Not Started | Vernost API; Salesforce
10 | AI Decision Engine MVP | Phase 2 | 31-Jan-2027 | Lakshmi Gopalakrishnan | Not Started | Data lake; model
11 | End-to-End Baggage Visibility GA | Phase 2 | 28-Feb-2027 | Meenakshi Jain | Not Started | BRS APIs
12 | OCC Dashboard GA | Phase 2 | 28-Feb-2027 | Lakshmi Gopalakrishnan | Not Started | AI engine; data
13 | Unified Boarding Pass GA (DEL/BOM/BLR/HYD) | Phase 2 | 31-Mar-2027 | Randhir Chambail | Not Started | Airport scanner adoption
14 | Phase 2 GA – All Scale Items | Phase 2 | 31-Mar-2027 | Swati Kothiyal / Raja Karmakar | Not Started | All Phase 2 epics
15 | Benefits Realization & Program Closure | Closure | 30-Apr-2027 | Raja Karmakar | Not Started | Post-launch NPS, KPI baseline

## Phase1_Quick_Wins
SL | Workstream | Epic / Feature | Granular Task | Description | Owner (Primary) | Owner (Support) | Dependency | Start Date | End Date | Duration (days) | Milestone | Deliverable | Status | % Complete | Remarks
1 | Journey Display | Date Change Indicators | Requirements & UX wireframe | Define UX for highlighting date changes in itinerary; finalize copy & visual treatment. | Sunil Kumar | Subham Srivastava | UX Research | 01-Jul-2026 | 08-Jul-2026 | 8 |  | Wireframes, copy deck | In Progress | 10 | Kick-off task
2 | Journey Display | Date Change Indicators | Backend logic for date diff calculation | Implement logic to detect itinerary date changes across segments and surface to clients. | Sunil Kumar | Subham Srivastava | PSS | 09-Jul-2026 | 22-Jul-2026 | 14 |  | Backend service | Not Started | 0
3 | Journey Display | Date Change Indicators | Frontend integration (iOS/Android/Web) | Surface badge / indicator across iOS, Android and Web channels. | Sunil Kumar | Subham Srivastava | Epic-1 backend | 23-Jul-2026 | 05-Aug-2026 | 14 |  | Client builds | Not Started | 0
4 | Journey Display | Date Change Indicators | QA & regression | Cross-platform QA and regression around itinerary screens. | Sunil Kumar | QA team | Client builds | 06-Aug-2026 | 12-Aug-2026 | 7 |  | QA report | Not Started | 0
5 | Journey Display | Date Change Indicators | Rollout (10% → 100%) | Phased rollout with monitoring on crash, conversion and NPS. | Sunil Kumar | Subham Srivastava | QA sign-off | 13-Aug-2026 | 20-Aug-2026 | 8 | Y | 100% GA | Not Started | 0
6 | Journey Display | Total Journey Duration & Layover Banner | Wireframe & copy approval | Visual + copy treatment for total journey duration with layover details. | Sunil Kumar | Heena Malhotra | - | 01-Jul-2026 | 10-Jul-2026 | 10 |  | Approved wireframes | Not Started | 0
7 | Journey Display | Total Journey Duration & Layover Banner | PSS data pull for layover | Confirm reliable source for layover times (PSS / sched data). | Subham Srivastava | Sunil Kumar | PSS | 11-Jul-2026 | 22-Jul-2026 | 12 |  | Data contract | Not Started | 0
8 | Journey Display | Total Journey Duration & Layover Banner | UI dev | Build banner UI across app & web. | Sunil Kumar | Subham Srivastava | Data contract | 23-Jul-2026 | 10-Aug-2026 | 19 |  | Banner component | Not Started | 0
9 | Journey Display | Total Journey Duration & Layover Banner | A/B testing | Run A/B to validate impact on customer comprehension. | Sunil Kumar | Analytics | Banner component | 11-Aug-2026 | 24-Aug-2026 | 14 |  | A/B report | Not Started | 0
10 | Journey Display | Total Journey Duration & Layover Banner | GA release | Full rollout post A/B success. | Sunil Kumar | Subham Srivastava | A/B report | 25-Aug-2026 | 31-Aug-2026 | 7 | Y | GA build | Not Started | 0
11 | Web Check-in | Single Click Check-in (Entire Journey) | Feasibility study with PSS team | Assess feasibility of single check-in covering all sectors of the PNR. | Sunil Kumar | PSS team | PSS | 01-Jul-2026 | 14-Jul-2026 | 14 |  | Feasibility note | In Progress | 15 | Critical Phase 1 item
12 | Web Check-in | Single Click Check-in (Entire Journey) | PNR & sector consolidation logic | Define rules for consolidating sectors into single check-in workflow. | Sunil Kumar | PSS team | Feasibility note | 15-Jul-2026 | 31-Jul-2026 | 17 |  | Logic spec | Not Started | 0
13 | Web Check-in | Single Click Check-in (Entire Journey) | API / Backend changes | Build backend APIs to support single click flow. | Sunil Kumar | Subham Srivastava | Logic spec | 01-Aug-2026 | 20-Aug-2026 | 20 |  | Backend APIs | Not Started | 0
14 | Web Check-in | Single Click Check-in (Entire Journey) | Web / App UI changes | Update web & app check-in screens. | Sunil Kumar | Subham Srivastava | Backend APIs | 21-Aug-2026 | 05-Sep-2026 | 16 |  | UI ready | Not Started | 0
15 | Web Check-in | Single Click Check-in (Entire Journey) | Regression with airport DCS | End-to-end regression including airport DCS scenarios. | Sunil Kumar | Airport Ops | UI ready | 06-Sep-2026 | 18-Sep-2026 | 13 |  | QA report | Not Started | 0
16 | Web Check-in | Single Click Check-in (Entire Journey) | Phased rollout | Phased rollout starting from low-volume sectors. | Sunil Kumar | Subham Srivastava | QA report | 19-Sep-2026 | 30-Sep-2026 | 12 | Y | GA | Not Started | 0
17 | Airport Maps | Static Airport Maps with Transfer Points | Content gathering DEL/BOM/BLR/HYD/MAA/CCU | Collect static maps and transfer point data from key hub airports. | Sunil Kumar | Subham Srivastava | Airports | 05-Jul-2026 | 25-Jul-2026 | 21 |  | Asset library | Not Started | 0
18 | Airport Maps | Static Airport Maps with Transfer Points | Map design & transfer point overlays | Design overlays showing transfer points and modes (walk, shuttle, bus). | Sunil Kumar | Subham Srivastava | Asset library | 26-Jul-2026 | 15-Aug-2026 | 21 |  | Final maps | Not Started | 0
19 | Airport Maps | Static Airport Maps with Transfer Points | In-app embed | Embed maps in app journey/connection screens. | Sunil Kumar | Subham Srivastava | Final maps | 16-Aug-2026 | 31-Aug-2026 | 16 |  | In-app integration | Not Started | 0
20 | Airport Maps | Static Airport Maps with Transfer Points | QA on map rendering | Cross-device QA on map rendering and zoom. | Sunil Kumar | QA team | Integration | 01-Sep-2026 | 12-Sep-2026 | 12 |  | QA sign-off | Not Started | 0
21 | Airport Maps | Static Airport Maps with Transfer Points | Release | GA release of static maps for hub airports. | Sunil Kumar | Subham Srivastava | QA sign-off | 13-Sep-2026 | 22-Sep-2026 | 10 | Y | GA build | Not Started | 0
22 | Timeline View | Step-by-step Journey Timeline | Information architecture | Define stages of connecting journey (arrive → transfer → security → boarding). | Sunil Kumar | Subham Srivastava | - | 01-Jul-2026 | 15-Jul-2026 | 15 |  | IA document | Not Started | 0
23 | Timeline View | Step-by-step Journey Timeline | Visual design & motion | Visual design including state progression and motion. | Sunil Kumar | Subham Srivastava | IA document | 16-Jul-2026 | 05-Aug-2026 | 21 |  | Design pack | Not Started | 0
24 | Timeline View | Step-by-step Journey Timeline | Frontend dev | Build timeline component on iOS/Android. | Sunil Kumar | Subham Srivastava | Design pack | 06-Aug-2026 | 31-Aug-2026 | 26 |  | Component | Not Started | 0
25 | Timeline View | Step-by-step Journey Timeline | QA | QA across device sizes & journeys (DOM, INT, layover variants). | QA team | Sunil Kumar | Component | 01-Sep-2026 | 12-Sep-2026 | 12 |  | QA sign-off | Not Started | 0
26 | Timeline View | Step-by-step Journey Timeline | Rollout | Phased rollout with NPS & engagement tracking. | Sunil Kumar | Subham Srivastava | QA sign-off | 13-Sep-2026 | 25-Sep-2026 | 13 | Y | GA | Not Started | 0
27 | Connection Risk Alerts | On Track / At Risk / Missed Notifications | Define risk rules (MCT, OTP, taxi) | Define rule-based logic considering MCT, OTP, taxi time, terminal change. | Subham Srivastava | Lakshmi Gopalakrishnan | NetOps | 01-Jul-2026 | 15-Jul-2026 | 15 |  | Rule book | Not Started | 0
28 | Connection Risk Alerts | On Track / At Risk / Missed Notifications | Data pipeline from NetOps & DCS | Build real-time data pipeline from NetOps & DCS to risk engine. | Subham Srivastava | NetOps | Rule book | 16-Jul-2026 | 05-Aug-2026 | 21 |  | Data pipeline | Not Started | 0
29 | Connection Risk Alerts | On Track / At Risk / Missed Notifications | Notification engine (push, WhatsApp, SMS) | Multi-channel notification engine with templating. | Subham Srivastava | Heena Malhotra | WA API | 20-Jul-2026 | 20-Aug-2026 | 32 |  | Notif engine | Not Started | 0
30 | Connection Risk Alerts | On Track / At Risk / Missed Notifications | Customer messaging & language approval | Approve tone, language, and translations of alerts. | Heena Malhotra | Raja Karmakar | Notif engine | 15-Aug-2026 | 31-Aug-2026 | 17 |  | Approved templates | Not Started | 0
31 | Connection Risk Alerts | On Track / At Risk / Missed Notifications | End-to-end testing | UAT across booking, ops disruption & recovery scenarios. | Subham Srivastava | QA team | Approved templates | 01-Sep-2026 | 15-Sep-2026 | 15 |  | UAT sign-off | Not Started | 0
32 | Connection Risk Alerts | On Track / At Risk / Missed Notifications | Pilot DEL→BOM, then scale | Pilot at DEL→BOM hub then scale to other hubs. | Subham Srivastava | Raja Karmakar | UAT sign-off | 16-Sep-2026 | 30-Sep-2026 | 15 | Y | Pilot live | Not Started | 0
33 | Gate & Belt | Gate / Baggage Belt Notifications | Airport API discovery (DIAL/MIAL/BIAL/HYD) | Identify airports with gate/belt APIs and data formats. | Subham Srivastava | Lakshmi Gopalakrishnan | Airports | 01-Jul-2026 | 20-Jul-2026 | 20 |  | API inventory | Not Started | 0
34 | Gate & Belt | Gate / Baggage Belt Notifications | Integration & data refresh logic | Integrate APIs with appropriate refresh cadence. | Subham Srivastava | Lakshmi Gopalakrishnan | API inventory | 21-Jul-2026 | 15-Aug-2026 | 26 |  | Integration | Not Started | 0
35 | Gate & Belt | Gate / Baggage Belt Notifications | Display in app (post-landing) | Surface gate & belt info in app post-landing screen. | Subham Srivastava | Sunil Kumar | Integration | 16-Aug-2026 | 05-Sep-2026 | 21 |  | App UI | Not Started | 0
36 | Gate & Belt | Gate / Baggage Belt Notifications | Fallback messaging when API down | Graceful fallback when airport API unavailable. | Heena Malhotra | Subham Srivastava | App UI | 06-Sep-2026 | 15-Sep-2026 | 10 |  | Fallback flow | Not Started | 0
37 | Gate & Belt | Gate / Baggage Belt Notifications | Rollout | Phased rollout across hub airports. | Lakshmi Gopalakrishnan | Subham Srivastava | Fallback flow | 16-Sep-2026 | 30-Sep-2026 | 15 | Y | GA | Not Started | 0
38 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) | Tier eligibility logic | Confirm tier eligibility rules with Loyalty/Marketing. | Sunil Kumar | Chakshu Garg | Loyalty | 01-Jul-2026 | 15-Jul-2026 | 15 |  | Logic doc | Not Started | 0
39 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) | UI badge design | Design tier badges & Heart marker for connecting flows. | Sunil Kumar | Subham Srivastava | - | 16-Jul-2026 | 31-Jul-2026 | 16 |  | Badge assets | Not Started | 0
40 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) | Backend tagging in customer profile | Tag customer profile with BluChip tier. | Sunil Kumar | Subham Srivastava | PSS/CRM | 01-Aug-2026 | 20-Aug-2026 | 20 |  | Profile service | Not Started | 0
41 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) | Touchpoint integration (BP, app) | Surface tier on boarding pass and app touchpoints. | Subham Srivastava | Sunil Kumar | Profile service | 21-Aug-2026 | 12-Sep-2026 | 23 |  | Integrated touchpoints | Not Started | 0
42 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) | Rollout | Phased rollout across customer base. | Sunil Kumar | Chakshu Garg | Integrated touchpoints | 13-Sep-2026 | 25-Sep-2026 | 13 | Y | GA | Not Started | 0
43 | Terminal Guidance | T2T Transfer & Shuttle Info | Content from airports (DEL T1/T3, BOM T1/T2) | Compile T2T transfer info and shuttle timings. | Sunil Kumar | Subham Srivastava | Airports | 10-Jul-2026 | 31-Jul-2026 | 22 |  | Content pack | Not Started | 0
44 | Terminal Guidance | T2T Transfer & Shuttle Info | In-app static content | Embed static T2T content in app. | Sunil Kumar | Subham Srivastava | Content pack | 01-Aug-2026 | 20-Aug-2026 | 20 |  | In-app content | Not Started | 0
45 | Terminal Guidance | T2T Transfer & Shuttle Info | Dynamic shuttle timing (where available) | Where APIs exist, surface dynamic shuttle timings. | Subham Srivastava | Airports | Airport API | 21-Aug-2026 | 15-Sep-2026 | 26 |  | Dynamic timings | Not Started | 0
46 | Terminal Guidance | T2T Transfer & Shuttle Info | Release | GA release. | Sunil Kumar | Subham Srivastava | Dynamic timings | 16-Sep-2026 | 28-Sep-2026 | 13 | Y | GA | Not Started | 0
47 | International | First Port of Entry Baggage Guidance | Identify intl-to-domestic PNRs | Identify PNRs that require baggage collection at first port of entry. | Sunil Kumar | Subham Srivastava | PSS | 05-Jul-2026 | 20-Jul-2026 | 16 |  | Tag logic | Not Started | 0
48 | International | First Port of Entry Baggage Guidance | Content creation (multi-lingual) | Create customer-facing content in English, Hindi & key regional languages. | Heena Malhotra | Sunil Kumar | Tag logic | 21-Jul-2026 | 15-Aug-2026 | 26 |  | Content pack | Not Started | 0
49 | International | First Port of Entry Baggage Guidance | Trigger logic post-landing notification | Trigger notification post-landing for relevant PNRs. | Subham Srivastava | Sunil Kumar | Content pack | 16-Aug-2026 | 10-Sep-2026 | 26 |  | Trigger engine | Not Started | 0
50 | International | First Port of Entry Baggage Guidance | Release | GA across applicable international arrivals. | Sunil Kumar | Subham Srivastava | Trigger engine | 11-Sep-2026 | 25-Sep-2026 | 15 | Y | GA | Not Started | 0
51 | Prototype | UI Prototype – All Phase 1 Use Cases | Figma wireframes | Wireframes covering all Phase 1 use cases. | Sunil Kumar | Subham Srivastava | - | 01-Jul-2026 | 12-Jul-2026 | 12 |  | Wireframes | In Progress | 20
52 | Prototype | UI Prototype – All Phase 1 Use Cases | Clickable prototype | Build interactive Figma prototype. | Sunil Kumar | Subham Srivastava | Wireframes | 13-Jul-2026 | 24-Jul-2026 | 12 |  | Prototype | Not Started | 0
53 | Prototype | UI Prototype – All Phase 1 Use Cases | Internal stakeholder review | Review with CX, Digital, Loyalty & Ops. | Raja Karmakar | Charu Verma | Prototype | 25-Jul-2026 | 29-Jul-2026 | 5 |  | Review notes | Not Started | 0
54 | Prototype | UI Prototype – All Phase 1 Use Cases | Sign-off | Final sign-off by sponsors. | Summi Sharma | Charu Verma | Review notes | 30-Jul-2026 | 31-Jul-2026 | 2 | Y | Sign-off | Not Started | 0

## Phase2_Scale_Differentiate
SL | Workstream | Epic / Feature | Granular Task | Description | Owner (Primary) | Owner (Support) | Dependency | Start Date | End Date | Duration (days) | Milestone | Deliverable | Status | % Complete | Remarks
1 | Boarding Pass | Unified Digital BP with Dynamic QR | Feasibility & IATA compliance review | Assess feasibility & IATA BCBP compliance for dynamic QR-based unified BP. | Randhir Chambail | Subham Srivastava | IATA standards | 01-Oct-2026 | 15-Oct-2026 | 15 |  | Feasibility note | Not Started | 0
2 | Boarding Pass | Unified Digital BP with Dynamic QR | Dynamic QR engine design | Design dynamic QR generation & activation engine. | Randhir Chambail | Subham Srivastava | Feasibility | 16-Oct-2026 | 15-Nov-2026 | 31 |  | Engine design | Not Started | 0
3 | Boarding Pass | Unified Digital BP with Dynamic QR | Integration with airport scanners | Integrate with airport scanner systems. | Randhir Chambail | Subham Srivastava | Airports | 16-Nov-2026 | 15-Dec-2026 | 30 |  | Integration | Not Started | 0
4 | Boarding Pass | Unified Digital BP with Dynamic QR | TIGO/LDC contingency scenarios | Test contingency with TIGO / Local DCS scenarios. | Randhir Chambail | Vinay Yadav | Integration | 01-Dec-2026 | 20-Dec-2026 | 20 |  | Contingency tested | Not Started | 0
5 | Boarding Pass | Unified Digital BP with Dynamic QR | Pilot at DEL | Pilot at DEL with controlled rollout. | Randhir Chambail | Subham Srivastava | Contingency | 21-Dec-2026 | 31-Dec-2026 | 11 | Y | Pilot live | Not Started | 0
6 | Boarding Pass | Unified Digital BP with Dynamic QR | Scale to BOM/BLR/HYD & GA | Scale to other hubs and GA. | Randhir Chambail | Subham Srivastava | Pilot success | 01-Jan-2027 | 31-Mar-2027 | 90 | Y | GA | Not Started | 0
7 | Boarding Pass | Boarding Pass Modernization | Visual redesign | Redesign digital BP visuals. | Sunil Kumar | Subham Srivastava | - | 01-Oct-2026 | 31-Oct-2026 | 31 |  | Design pack | Not Started | 0
8 | Boarding Pass | Boarding Pass Modernization | Cross-platform alignment (app/web/email/PDF) | Standardize BP across all touchpoints. | Sunil Kumar | Subham Srivastava | Design pack | 01-Nov-2026 | 30-Nov-2026 | 30 |  | Standard library | Not Started | 0
9 | Boarding Pass | Boarding Pass Modernization | A/B testing | A/B test redesigned BP. | Sunil Kumar | Analytics | Standard library | 01-Dec-2026 | 31-Dec-2026 | 31 |  | A/B report | Not Started | 0
10 | Boarding Pass | Boarding Pass Modernization | Rollout | Full rollout. | Sunil Kumar | Subham Srivastava | A/B success | 01-Jan-2027 | 31-Jan-2027 | 31 | Y | GA | Not Started | 0
11 | Baggage Visibility | End-to-End Baggage Visibility | BRS provider discovery | Identify BRS providers per station. | Meenakshi Jain | Randhir Chambail | BRS | 01-Oct-2026 | 20-Oct-2026 | 20 |  | Provider list | Not Started | 0
12 | Baggage Visibility | End-to-End Baggage Visibility | API agreements DIAL/MIAL/BIAL/HYD | Sign API/data agreements with hub airports. | Subham Srivastava | Meenakshi Jain | Airports | 21-Oct-2026 | 30-Nov-2026 | 41 |  | Signed MoUs | Not Started | 0
13 | Baggage Visibility | End-to-End Baggage Visibility | Integration | Integrate BRS feeds. | Subham Srivastava | Sunil Kumar | MoUs | 01-Dec-2026 | 15-Jan-2027 | 46 |  | Integrated feed | Not Started | 0
14 | Baggage Visibility | End-to-End Baggage Visibility | Status engine | Build baggage status engine with state machine. | Subham Srivastava | Meenakshi Jain | Feed | 15-Dec-2026 | 31-Jan-2027 | 48 |  | Status engine | Not Started | 0
15 | Baggage Visibility | End-to-End Baggage Visibility | In-app UI | Build customer-facing baggage tracking screen. | Sunil Kumar | Subham Srivastava | Engine | 01-Feb-2027 | 20-Feb-2027 | 20 |  | App UI | Not Started | 0
16 | Baggage Visibility | End-to-End Baggage Visibility | Pilot & GA | Pilot at DEL, then GA across hubs. | Meenakshi Jain | Subham Srivastava | UI | 21-Feb-2027 | 28-Feb-2027 | 8 | Y | GA | Not Started | 0
17 | Auto-Recovery | Rebooking & Refund Automation | Rebooking rules engine | Build rules engine for auto rebooking. | Lakshmi Gopalakrishnan | Subham Srivastava | - | 01-Oct-2026 | 31-Oct-2026 | 31 |  | Rules engine | Not Started | 0
18 | Auto-Recovery | Rebooking & Refund Automation | Solution Tek integration | Integrate with Solution Tek workflow. | Lakshmi Gopalakrishnan | IT | Solution Tek | 01-Nov-2026 | 15-Dec-2026 | 45 |  | Integration | Not Started | 0
19 | Auto-Recovery | Rebooking & Refund Automation | Refund automation | Automate refund workflows. | Lakshmi Gopalakrishnan | Finance | - | 15-Nov-2026 | 15-Jan-2027 | 62 |  | Refund automation | Not Started | 0
20 | Auto-Recovery | Rebooking & Refund Automation | App flow | Customer-facing app flow for recovery options. | Sunil Kumar | Lakshmi Gopalakrishnan | Engine | 01-Jan-2027 | 31-Jan-2027 | 31 |  | App flow | Not Started | 0
21 | Auto-Recovery | Rebooking & Refund Automation | Pilot & GA | Pilot then GA. | Lakshmi Gopalakrishnan | Raja Karmakar | App flow | 01-Feb-2027 | 28-Feb-2027 | 28 | Y | GA | Not Started | 0
22 | Hotel & Voucher | Hotel & Voucher Integration | Vernost API integration | Integrate with Vernost APIs. | Lakshmi Gopalakrishnan | IT | Vernost | 01-Oct-2026 | 15-Nov-2026 | 46 |  | Integration | Not Started | 0
23 | Hotel & Voucher | Hotel & Voucher Integration | Voucher engine | Build voucher engine. | Lakshmi Gopalakrishnan | Finance | - | 15-Oct-2026 | 30-Nov-2026 | 47 |  | Voucher engine | Not Started | 0
24 | Hotel & Voucher | Hotel & Voucher Integration | Salesforce hooks | Salesforce hooks for case management. | Lakshmi Gopalakrishnan | IT | Salesforce | 15-Nov-2026 | 15-Dec-2026 | 31 |  | SFDC integration | Not Started | 0
25 | Hotel & Voucher | Hotel & Voucher Integration | App flow | Customer flow to claim hotel & voucher. | Sunil Kumar | Lakshmi Gopalakrishnan | - | 01-Dec-2026 | 25-Dec-2026 | 25 |  | App flow | Not Started | 0
26 | Hotel & Voucher | Hotel & Voucher Integration | Pilot & GA | Pilot at a hub then GA. | Lakshmi Gopalakrishnan | Raja Karmakar | App flow | 20-Dec-2026 | 31-Dec-2026 | 12 | Y | GA | Not Started | 0
27 | AI & OCC | AI Decision Engine & OCC Dashboard | Data lake setup | Set up data lake & ingestion pipelines. | Lakshmi Gopalakrishnan | Jochen Hoesch | Data platform | 01-Oct-2026 | 15-Nov-2026 | 46 |  | Data lake | Not Started | 0
28 | AI & OCC | AI Decision Engine & OCC Dashboard | Feature engineering | Define & build features for connection risk model. | Lakshmi Gopalakrishnan | Jochen Hoesch | Data lake | 01-Nov-2026 | 15-Dec-2026 | 45 |  | Feature store | Not Started | 0
29 | AI & OCC | AI Decision Engine & OCC Dashboard | Model training (connection risk) | Train & validate model with shadow mode. | Lakshmi Gopalakrishnan | Jochen Hoesch | Features | 01-Dec-2026 | 15-Jan-2027 | 46 |  | Model | Not Started | 0
30 | AI & OCC | AI Decision Engine & OCC Dashboard | Decision tree for OCC | Define decision tree for OCC actions. | Lakshmi Gopalakrishnan | Naresh Rao | Model | 01-Jan-2027 | 31-Jan-2027 | 31 |  | Decision tree | Not Started | 0
31 | AI & OCC | AI Decision Engine & OCC Dashboard | Dashboard build | Build OCC dashboard with KPIs. | Lakshmi Gopalakrishnan | Subham Srivastava | Tree | 15-Jan-2027 | 20-Feb-2027 | 37 |  | Dashboard | Not Started | 0
32 | AI & OCC | AI Decision Engine & OCC Dashboard | Pilot & GA | Pilot in OCC then GA. | Lakshmi Gopalakrishnan | Raja Karmakar | Dashboard | 21-Feb-2027 | 28-Feb-2027 | 8 | Y | GA | Not Started | 0
33 | Campaign | Paperless Boarding Campaign | Campaign strategy | Define paperless boarding campaign strategy. | Raja Karmakar | Heena Malhotra | - | 01-Oct-2026 | 31-Oct-2026 | 31 |  | Strategy doc | Not Started | 0
34 | Campaign | Paperless Boarding Campaign | Creative development | Develop creatives across channels. | Heena Malhotra | Chakshu Garg | Strategy | 01-Nov-2026 | 15-Dec-2026 | 45 |  | Creatives | Not Started | 0
35 | Campaign | Paperless Boarding Campaign | Channel plan (app/email/WA/Social) | Channel plan and segmentation. | Heena Malhotra | Chakshu Garg | Creatives | 01-Dec-2026 | 31-Dec-2026 | 31 |  | Channel plan | Not Started | 0
36 | Campaign | Paperless Boarding Campaign | Launch | Launch campaign. | Raja Karmakar | Heena Malhotra | Channel plan | 15-Jan-2027 | 15-Feb-2027 | 32 |  | Live campaign | Not Started | 0
37 | Campaign | Paperless Boarding Campaign | Measurement & iterate | Measure adoption and iterate. | Heena Malhotra | Analytics | Live campaign | 16-Feb-2027 | 31-Mar-2027 | 44 | Y | Adoption report | Not Started | 0
38 | Connection Tags | Short / Long Connection Tagging | Logic review | Review current tagging logic. | Subham Srivastava | Randhir Chambail | - | 01-Oct-2026 | 20-Oct-2026 | 20 |  | Review doc | Not Started | 0
39 | Connection Tags | Short / Long Connection Tagging | New tagging schema | Define modernized schema. | Subham Srivastava | Sunil Kumar | Review | 21-Oct-2026 | 15-Nov-2026 | 26 |  | Schema | Not Started | 0
40 | Connection Tags | Short / Long Connection Tagging | PSS update | Apply schema in PSS / data. | Subham Srivastava | PSS team | PSS | 16-Nov-2026 | 30-Nov-2026 | 15 |  | PSS update | Not Started | 0
41 | Connection Tags | Short / Long Connection Tagging | Rollout | Rollout new tags across systems. | Subham Srivastava | Randhir Chambail | PSS update | 01-Dec-2026 | 15-Dec-2026 | 15 | Y | GA | Not Started | 0
42 | Airport APIs | Airport Map APIs (DIAL/MIAL/BIAL) | Partner engagement | Engage with airport operators. | Subham Srivastava | Charu Verma | Airports | 01-Oct-2026 | 31-Oct-2026 | 31 |  | Engagement | Not Started | 0
43 | Airport APIs | Airport Map APIs (DIAL/MIAL/BIAL) | Contract & data agreement | Sign contracts & data agreements. | Subham Srivastava | Legal | Engagement | 01-Nov-2026 | 15-Dec-2026 | 45 |  | Contracts | Not Started | 0
44 | Airport APIs | Airport Map APIs (DIAL/MIAL/BIAL) | Integration | Integrate APIs into product. | Subham Srivastava | Sunil Kumar | Contracts | 15-Dec-2026 | 15-Feb-2027 | 63 |  | Integration | Not Started | 0
45 | Airport APIs | Airport Map APIs (DIAL/MIAL/BIAL) | Replace static maps | Replace static maps with dynamic. | Sunil Kumar | Subham Srivastava | Integration | 16-Feb-2027 | 31-Mar-2027 | 44 | Y | GA | Not Started | 0
46 | Baggage APIs | Baggage APIs from BRS providers | Provider shortlist | Shortlist BRS providers. | Randhir Chambail | Subham Srivastava | - | 01-Oct-2026 | 20-Oct-2026 | 20 |  | Shortlist | Not Started | 0
47 | Baggage APIs | Baggage APIs from BRS providers | Commercial | Commercial negotiations. | Randhir Chambail | Procurement | Shortlist | 21-Oct-2026 | 15-Dec-2026 | 56 |  | Contract | Not Started | 0
48 | Baggage APIs | Baggage APIs from BRS providers | Integration | Integrate BRS APIs. | Subham Srivastava | Randhir Chambail | Contract | 16-Dec-2026 | 15-Feb-2027 | 62 |  | Integration | Not Started | 0
49 | Baggage APIs | Baggage APIs from BRS providers | Testing | End-to-end testing. | Subham Srivastava | QA | Integration | 16-Feb-2027 | 15-Mar-2027 | 28 | Y | QA sign-off | Not Started | 0

## Gantt_Phase1
Connections Enhancement Program – Phase 1 Quick Wins Gantt (Jul – Sep 2026)
Task Details | [7 empty] | Jul 2026 |  |  |  |  | Aug 2026 |  |  |  | Sep 2026
SL | Workstream | Epic / Task | Owner | Start | End | Days | Status | W1 01-Jul | W2 08-Jul | W3 15-Jul | W4 22-Jul | W5 29-Jul | W6 05-Aug | W7 12-Aug | W8 19-Aug | W9 26-Aug | W10 02-Sep | W11 09-Sep | W12 16-Sep | W13 23-Sep | W14 30-Sep
1 | Journey Display | Date Change Indicators — Requirements & UX wireframe | Sunil Kumar | 01-Jul-2026 | 08-Jul-2026 | 8 | In Progress
2 | Journey Display | Date Change Indicators — Backend logic for date diff calculation | Sunil Kumar | 09-Jul-2026 | 22-Jul-2026 | 14 | Not Started
3 | Journey Display | Date Change Indicators — Frontend integration (iOS/Android/Web) | Sunil Kumar | 23-Jul-2026 | 05-Aug-2026 | 14 | Not Started
4 | Journey Display | Date Change Indicators — QA & regression | Sunil Kumar | 06-Aug-2026 | 12-Aug-2026 | 7 | Not Started
5 | Journey Display | Date Change Indicators — Rollout (10% → 100%) | Sunil Kumar | 13-Aug-2026 | 20-Aug-2026 | 8 | Not Started | [7 empty] | ◆
6 | Journey Display | Total Journey Duration & Layover Banner — Wireframe & copy approval | Sunil Kumar | 01-Jul-2026 | 10-Jul-2026 | 10 | Not Started
7 | Journey Display | Total Journey Duration & Layover Banner — PSS data pull for layover | Subham Srivastava | 11-Jul-2026 | 22-Jul-2026 | 12 | Not Started
8 | Journey Display | Total Journey Duration & Layover Banner — UI dev | Sunil Kumar | 23-Jul-2026 | 10-Aug-2026 | 19 | Not Started
9 | Journey Display | Total Journey Duration & Layover Banner — A/B testing | Sunil Kumar | 11-Aug-2026 | 24-Aug-2026 | 14 | Not Started
10 | Journey Display | Total Journey Duration & Layover Banner — GA release | Sunil Kumar | 25-Aug-2026 | 31-Aug-2026 | 7 | Not Started | [8 empty] | ◆
11 | Web Check-in | Single Click Check-in (Entire Journey) — Feasibility study with PSS team | Sunil Kumar | 01-Jul-2026 | 14-Jul-2026 | 14 | In Progress
12 | Web Check-in | Single Click Check-in (Entire Journey) — PNR & sector consolidation logic | Sunil Kumar | 15-Jul-2026 | 31-Jul-2026 | 17 | Not Started
13 | Web Check-in | Single Click Check-in (Entire Journey) — API / Backend changes | Sunil Kumar | 01-Aug-2026 | 20-Aug-2026 | 20 | Not Started
14 | Web Check-in | Single Click Check-in (Entire Journey) — Web / App UI changes | Sunil Kumar | 21-Aug-2026 | 05-Sep-2026 | 16 | Not Started
15 | Web Check-in | Single Click Check-in (Entire Journey) — Regression with airport DCS | Sunil Kumar | 06-Sep-2026 | 18-Sep-2026 | 13 | Not Started
16 | Web Check-in | Single Click Check-in (Entire Journey) — Phased rollout | Sunil Kumar | 19-Sep-2026 | 30-Sep-2026 | 12 | Not Started | [13 empty] | ◆
17 | Airport Maps | Static Airport Maps with Transfer Points — Content gathering DEL/BOM/BLR/HYD/MAA/CCU | Sunil Kumar | 05-Jul-2026 | 25-Jul-2026 | 21 | Not Started
18 | Airport Maps | Static Airport Maps with Transfer Points — Map design & transfer point overlays | Sunil Kumar | 26-Jul-2026 | 15-Aug-2026 | 21 | Not Started
19 | Airport Maps | Static Airport Maps with Transfer Points — In-app embed | Sunil Kumar | 16-Aug-2026 | 31-Aug-2026 | 16 | Not Started
20 | Airport Maps | Static Airport Maps with Transfer Points — QA on map rendering | Sunil Kumar | 01-Sep-2026 | 12-Sep-2026 | 12 | Not Started
21 | Airport Maps | Static Airport Maps with Transfer Points — Release | Sunil Kumar | 13-Sep-2026 | 22-Sep-2026 | 10 | Not Started | [11 empty] | ◆
22 | Timeline View | Step-by-step Journey Timeline — Information architecture | Sunil Kumar | 01-Jul-2026 | 15-Jul-2026 | 15 | Not Started
23 | Timeline View | Step-by-step Journey Timeline — Visual design & motion | Sunil Kumar | 16-Jul-2026 | 05-Aug-2026 | 21 | Not Started
24 | Timeline View | Step-by-step Journey Timeline — Frontend dev | Sunil Kumar | 06-Aug-2026 | 31-Aug-2026 | 26 | Not Started
25 | Timeline View | Step-by-step Journey Timeline — QA | QA team | 01-Sep-2026 | 12-Sep-2026 | 12 | Not Started
26 | Timeline View | Step-by-step Journey Timeline — Rollout | Sunil Kumar | 13-Sep-2026 | 25-Sep-2026 | 13 | Not Started | [12 empty] | ◆
27 | Connection Risk Alerts | On Track / At Risk / Missed Notifications — Define risk rules (MCT, OTP, taxi) | Subham Srivastava | 01-Jul-2026 | 15-Jul-2026 | 15 | Not Started
28 | Connection Risk Alerts | On Track / At Risk / Missed Notifications — Data pipeline from NetOps & DCS | Subham Srivastava | 16-Jul-2026 | 05-Aug-2026 | 21 | Not Started
29 | Connection Risk Alerts | On Track / At Risk / Missed Notifications — Notification engine (push, WhatsApp, SMS) | Subham Srivastava | 20-Jul-2026 | 20-Aug-2026 | 32 | Not Started
30 | Connection Risk Alerts | On Track / At Risk / Missed Notifications — Customer messaging & language approval | Heena Malhotra | 15-Aug-2026 | 31-Aug-2026 | 17 | Not Started
31 | Connection Risk Alerts | On Track / At Risk / Missed Notifications — End-to-end testing | Subham Srivastava | 01-Sep-2026 | 15-Sep-2026 | 15 | Not Started
32 | Connection Risk Alerts | On Track / At Risk / Missed Notifications — Pilot DEL→BOM, then scale | Subham Srivastava | 16-Sep-2026 | 30-Sep-2026 | 15 | Not Started | [13 empty] | ◆
33 | Gate & Belt | Gate / Baggage Belt Notifications — Airport API discovery (DIAL/MIAL/BIAL/HYD) | Subham Srivastava | 01-Jul-2026 | 20-Jul-2026 | 20 | Not Started
34 | Gate & Belt | Gate / Baggage Belt Notifications — Integration & data refresh logic | Subham Srivastava | 21-Jul-2026 | 15-Aug-2026 | 26 | Not Started
35 | Gate & Belt | Gate / Baggage Belt Notifications — Display in app (post-landing) | Subham Srivastava | 16-Aug-2026 | 05-Sep-2026 | 21 | Not Started
36 | Gate & Belt | Gate / Baggage Belt Notifications — Fallback messaging when API down | Heena Malhotra | 06-Sep-2026 | 15-Sep-2026 | 10 | Not Started
37 | Gate & Belt | Gate / Baggage Belt Notifications — Rollout | Lakshmi Gopalakrishnan | 16-Sep-2026 | 30-Sep-2026 | 15 | Not Started | [13 empty] | ◆
38 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) — Tier eligibility logic | Sunil Kumar | 01-Jul-2026 | 15-Jul-2026 | 15 | Not Started
39 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) — UI badge design | Sunil Kumar | 16-Jul-2026 | 31-Jul-2026 | 16 | Not Started
40 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) — Backend tagging in customer profile | Sunil Kumar | 01-Aug-2026 | 20-Aug-2026 | 20 | Not Started
41 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) — Touchpoint integration (BP, app) | Subham Srivastava | 21-Aug-2026 | 12-Sep-2026 | 23 | Not Started
42 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) — Rollout | Sunil Kumar | 13-Sep-2026 | 25-Sep-2026 | 13 | Not Started | [12 empty] | ◆
43 | Terminal Guidance | T2T Transfer & Shuttle Info — Content from airports (DEL T1/T3, BOM T1/T2) | Sunil Kumar | 10-Jul-2026 | 31-Jul-2026 | 22 | Not Started
44 | Terminal Guidance | T2T Transfer & Shuttle Info — In-app static content | Sunil Kumar | 01-Aug-2026 | 20-Aug-2026 | 20 | Not Started
45 | Terminal Guidance | T2T Transfer & Shuttle Info — Dynamic shuttle timing (where available) | Subham Srivastava | 21-Aug-2026 | 15-Sep-2026 | 26 | Not Started
46 | Terminal Guidance | T2T Transfer & Shuttle Info — Release | Sunil Kumar | 16-Sep-2026 | 28-Sep-2026 | 13 | Not Started | [12 empty] | ◆
47 | International | First Port of Entry Baggage Guidance — Identify intl-to-domestic PNRs | Sunil Kumar | 05-Jul-2026 | 20-Jul-2026 | 16 | Not Started
48 | International | First Port of Entry Baggage Guidance — Content creation (multi-lingual) | Heena Malhotra | 21-Jul-2026 | 15-Aug-2026 | 26 | Not Started
49 | International | First Port of Entry Baggage Guidance — Trigger logic post-landing notification | Subham Srivastava | 16-Aug-2026 | 10-Sep-2026 | 26 | Not Started
50 | International | First Port of Entry Baggage Guidance — Release | Sunil Kumar | 11-Sep-2026 | 25-Sep-2026 | 15 | Not Started | [12 empty] | ◆
51 | Prototype | UI Prototype – All Phase 1 Use Cases — Figma wireframes | Sunil Kumar | 01-Jul-2026 | 12-Jul-2026 | 12 | In Progress
52 | Prototype | UI Prototype – All Phase 1 Use Cases — Clickable prototype | Sunil Kumar | 13-Jul-2026 | 24-Jul-2026 | 12 | Not Started
53 | Prototype | UI Prototype – All Phase 1 Use Cases — Internal stakeholder review | Raja Karmakar | 25-Jul-2026 | 29-Jul-2026 | 5 | Not Started
54 | Prototype | UI Prototype – All Phase 1 Use Cases — Sign-off | Summi Sharma | 30-Jul-2026 | 31-Jul-2026 | 2 | Not Started |  |  |  |  | ◆
Workstream Legend:
| Journey Display |  |  | Gate & Belt
| Web Check-in |  |  | Loyalty
| Airport Maps |  |  | Terminal Guidance
| Timeline View |  |  | International
| Connection Risk Alerts |  |  | Prototype

## Gantt_Phase2
Connections Enhancement Program – Phase 2 Scale & Differentiate Gantt (Oct 2026 – Mar 2027)
Task Details | [7 empty] | Oct 2026 |  |  |  |  | Nov 2026 |  |  |  | Dec 2026 |  |  |  |  | Jan 2027 |  |  |  | Feb 2027 |  |  |  | Mar 2027 |  |  |  | Apr 2027
SL | Workstream | Epic / Task | Owner | Start | End | Days | Status | W1 01-Oct | W2 08-Oct | W3 15-Oct | W4 22-Oct | W5 29-Oct | W6 05-Nov | W7 12-Nov | W8 19-Nov | W9 26-Nov | W10 03-Dec | W11 10-Dec | W12 17-Dec | W13 24-Dec | W14 31-Dec | W15 07-Jan | W16 14-Jan | W17 21-Jan | W18 28-Jan | W19 04-Feb | W20 11-Feb | W21 18-Feb | W22 25-Feb | W23 04-Mar | W24 11-Mar | W25 18-Mar | W26 25-Mar | W27 01-Apr
1 | Boarding Pass | Unified Digital BP with Dynamic QR — Feasibility & IATA compliance review | Randhir Chambail | 01-Oct-2026 | 15-Oct-2026 | 15 | Not Started
2 | Boarding Pass | Unified Digital BP with Dynamic QR — Dynamic QR engine design | Randhir Chambail | 16-Oct-2026 | 15-Nov-2026 | 31 | Not Started
3 | Boarding Pass | Unified Digital BP with Dynamic QR — Integration with airport scanners | Randhir Chambail | 16-Nov-2026 | 15-Dec-2026 | 30 | Not Started
4 | Boarding Pass | Unified Digital BP with Dynamic QR — TIGO/LDC contingency scenarios | Randhir Chambail | 01-Dec-2026 | 20-Dec-2026 | 20 | Not Started
5 | Boarding Pass | Unified Digital BP with Dynamic QR — Pilot at DEL | Randhir Chambail | 21-Dec-2026 | 31-Dec-2026 | 11 | Not Started | [13 empty] | ◆
6 | Boarding Pass | Unified Digital BP with Dynamic QR — Scale to BOM/BLR/HYD & GA | Randhir Chambail | 01-Jan-2027 | 31-Mar-2027 | 90 | Not Started | [25 empty] | ◆
7 | Boarding Pass | Boarding Pass Modernization — Visual redesign | Sunil Kumar | 01-Oct-2026 | 31-Oct-2026 | 31 | Not Started
8 | Boarding Pass | Boarding Pass Modernization — Cross-platform alignment (app/web/email/PDF) | Sunil Kumar | 01-Nov-2026 | 30-Nov-2026 | 30 | Not Started
9 | Boarding Pass | Boarding Pass Modernization — A/B testing | Sunil Kumar | 01-Dec-2026 | 31-Dec-2026 | 31 | Not Started
10 | Boarding Pass | Boarding Pass Modernization — Rollout | Sunil Kumar | 01-Jan-2027 | 31-Jan-2027 | 31 | Not Started | [17 empty] | ◆
11 | Baggage Visibility | End-to-End Baggage Visibility — BRS provider discovery | Meenakshi Jain | 01-Oct-2026 | 20-Oct-2026 | 20 | Not Started
12 | Baggage Visibility | End-to-End Baggage Visibility — API agreements DIAL/MIAL/BIAL/HYD | Subham Srivastava | 21-Oct-2026 | 30-Nov-2026 | 41 | Not Started
13 | Baggage Visibility | End-to-End Baggage Visibility — Integration | Subham Srivastava | 01-Dec-2026 | 15-Jan-2027 | 46 | Not Started
14 | Baggage Visibility | End-to-End Baggage Visibility — Status engine | Subham Srivastava | 15-Dec-2026 | 31-Jan-2027 | 48 | Not Started
15 | Baggage Visibility | End-to-End Baggage Visibility — In-app UI | Sunil Kumar | 01-Feb-2027 | 20-Feb-2027 | 20 | Not Started
16 | Baggage Visibility | End-to-End Baggage Visibility — Pilot & GA | Meenakshi Jain | 21-Feb-2027 | 28-Feb-2027 | 8 | Not Started | [21 empty] | ◆
17 | Auto-Recovery | Rebooking & Refund Automation — Rebooking rules engine | Lakshmi Gopalakrishnan | 01-Oct-2026 | 31-Oct-2026 | 31 | Not Started
18 | Auto-Recovery | Rebooking & Refund Automation — Solution Tek integration | Lakshmi Gopalakrishnan | 01-Nov-2026 | 15-Dec-2026 | 45 | Not Started
19 | Auto-Recovery | Rebooking & Refund Automation — Refund automation | Lakshmi Gopalakrishnan | 15-Nov-2026 | 15-Jan-2027 | 62 | Not Started
20 | Auto-Recovery | Rebooking & Refund Automation — App flow | Sunil Kumar | 01-Jan-2027 | 31-Jan-2027 | 31 | Not Started
21 | Auto-Recovery | Rebooking & Refund Automation — Pilot & GA | Lakshmi Gopalakrishnan | 01-Feb-2027 | 28-Feb-2027 | 28 | Not Started | [21 empty] | ◆
22 | Hotel & Voucher | Hotel & Voucher Integration — Vernost API integration | Lakshmi Gopalakrishnan | 01-Oct-2026 | 15-Nov-2026 | 46 | Not Started
23 | Hotel & Voucher | Hotel & Voucher Integration — Voucher engine | Lakshmi Gopalakrishnan | 15-Oct-2026 | 30-Nov-2026 | 47 | Not Started
24 | Hotel & Voucher | Hotel & Voucher Integration — Salesforce hooks | Lakshmi Gopalakrishnan | 15-Nov-2026 | 15-Dec-2026 | 31 | Not Started
25 | Hotel & Voucher | Hotel & Voucher Integration — App flow | Sunil Kumar | 01-Dec-2026 | 25-Dec-2026 | 25 | Not Started
26 | Hotel & Voucher | Hotel & Voucher Integration — Pilot & GA | Lakshmi Gopalakrishnan | 20-Dec-2026 | 31-Dec-2026 | 12 | Not Started | [13 empty] | ◆
27 | AI & OCC | AI Decision Engine & OCC Dashboard — Data lake setup | Lakshmi Gopalakrishnan | 01-Oct-2026 | 15-Nov-2026 | 46 | Not Started
28 | AI & OCC | AI Decision Engine & OCC Dashboard — Feature engineering | Lakshmi Gopalakrishnan | 01-Nov-2026 | 15-Dec-2026 | 45 | Not Started
29 | AI & OCC | AI Decision Engine & OCC Dashboard — Model training (connection risk) | Lakshmi Gopalakrishnan | 01-Dec-2026 | 15-Jan-2027 | 46 | Not Started
30 | AI & OCC | AI Decision Engine & OCC Dashboard — Decision tree for OCC | Lakshmi Gopalakrishnan | 01-Jan-2027 | 31-Jan-2027 | 31 | Not Started
31 | AI & OCC | AI Decision Engine & OCC Dashboard — Dashboard build | Lakshmi Gopalakrishnan | 15-Jan-2027 | 20-Feb-2027 | 37 | Not Started
32 | AI & OCC | AI Decision Engine & OCC Dashboard — Pilot & GA | Lakshmi Gopalakrishnan | 21-Feb-2027 | 28-Feb-2027 | 8 | Not Started | [21 empty] | ◆
33 | Campaign | Paperless Boarding Campaign — Campaign strategy | Raja Karmakar | 01-Oct-2026 | 31-Oct-2026 | 31 | Not Started
34 | Campaign | Paperless Boarding Campaign — Creative development | Heena Malhotra | 01-Nov-2026 | 15-Dec-2026 | 45 | Not Started
35 | Campaign | Paperless Boarding Campaign — Channel plan (app/email/WA/Social) | Heena Malhotra | 01-Dec-2026 | 31-Dec-2026 | 31 | Not Started
36 | Campaign | Paperless Boarding Campaign — Launch | Raja Karmakar | 15-Jan-2027 | 15-Feb-2027 | 32 | Not Started
37 | Campaign | Paperless Boarding Campaign — Measurement & iterate | Heena Malhotra | 16-Feb-2027 | 31-Mar-2027 | 44 | Not Started | [25 empty] | ◆
38 | Connection Tags | Short / Long Connection Tagging — Logic review | Subham Srivastava | 01-Oct-2026 | 20-Oct-2026 | 20 | Not Started
39 | Connection Tags | Short / Long Connection Tagging — New tagging schema | Subham Srivastava | 21-Oct-2026 | 15-Nov-2026 | 26 | Not Started
40 | Connection Tags | Short / Long Connection Tagging — PSS update | Subham Srivastava | 16-Nov-2026 | 30-Nov-2026 | 15 | Not Started
41 | Connection Tags | Short / Long Connection Tagging — Rollout | Subham Srivastava | 01-Dec-2026 | 15-Dec-2026 | 15 | Not Started | [10 empty] | ◆
42 | Airport APIs | Airport Map APIs (DIAL/MIAL/BIAL) — Partner engagement | Subham Srivastava | 01-Oct-2026 | 31-Oct-2026 | 31 | Not Started
43 | Airport APIs | Airport Map APIs (DIAL/MIAL/BIAL) — Contract & data agreement | Subham Srivastava | 01-Nov-2026 | 15-Dec-2026 | 45 | Not Started
44 | Airport APIs | Airport Map APIs (DIAL/MIAL/BIAL) — Integration | Subham Srivastava | 15-Dec-2026 | 15-Feb-2027 | 63 | Not Started
45 | Airport APIs | Airport Map APIs (DIAL/MIAL/BIAL) — Replace static maps | Sunil Kumar | 16-Feb-2027 | 31-Mar-2027 | 44 | Not Started | [25 empty] | ◆
46 | Baggage APIs | Baggage APIs from BRS providers — Provider shortlist | Randhir Chambail | 01-Oct-2026 | 20-Oct-2026 | 20 | Not Started
47 | Baggage APIs | Baggage APIs from BRS providers — Commercial | Randhir Chambail | 21-Oct-2026 | 15-Dec-2026 | 56 | Not Started
48 | Baggage APIs | Baggage APIs from BRS providers — Integration | Subham Srivastava | 16-Dec-2026 | 15-Feb-2027 | 62 | Not Started
49 | Baggage APIs | Baggage APIs from BRS providers — Testing | Subham Srivastava | 16-Feb-2027 | 15-Mar-2027 | 28 | Not Started | [23 empty] | ◆
Workstream Legend:
| Boarding Pass |  |  | Campaign
| Baggage Visibility |  |  | Connection Tags
| Auto-Recovery |  |  | Airport APIs
| Hotel & Voucher |  |  | Baggage APIs
AI & OCC

## Gantt_Overall
Connections Enhancement Program – Overall Program Gantt (Jul 2026 – Apr 2027)
SL | Workstream | Epic / Milestone | Owner | Start | End | Days | Phase | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27
1 | Journey Display | Date Change Indicators | Sunil Kumar | 01-Jul-2026 | 20-Aug-2026 | 51 | Phase 1
2 | Journey Display | Total Journey Duration & Layover Banner | Sunil Kumar | 01-Jul-2026 | 31-Aug-2026 | 62 | Phase 1
3 | Web Check-in | Single Click Check-in (Entire Journey) | Sunil Kumar | 01-Jul-2026 | 30-Sep-2026 | 92 | Phase 1
4 | Airport Maps | Static Airport Maps with Transfer Points | Sunil Kumar | 05-Jul-2026 | 22-Sep-2026 | 80 | Phase 1
5 | Timeline View | Step-by-step Journey Timeline | Sunil Kumar | 01-Jul-2026 | 25-Sep-2026 | 87 | Phase 1
6 | Connection Risk Alerts | On Track / At Risk / Missed Notifications | Subham Srivastava | 01-Jul-2026 | 30-Sep-2026 | 92 | Phase 1
7 | Gate & Belt | Gate / Baggage Belt Notifications | Subham Srivastava | 01-Jul-2026 | 30-Sep-2026 | 92 | Phase 1
8 | Loyalty | BluChip (BLU1/BLU2/BLU3 + Heart) | Sunil Kumar | 01-Jul-2026 | 25-Sep-2026 | 87 | Phase 1
9 | Terminal Guidance | T2T Transfer & Shuttle Info | Sunil Kumar | 10-Jul-2026 | 28-Sep-2026 | 81 | Phase 1
10 | International | First Port of Entry Baggage Guidance | Sunil Kumar | 05-Jul-2026 | 25-Sep-2026 | 83 | Phase 1
11 | Prototype | UI Prototype – All Phase 1 Use Cases | Sunil Kumar | 01-Jul-2026 | 31-Jul-2026 | 31 | Phase 1
12 | Boarding Pass | Unified Digital BP with Dynamic QR | Randhir Chambail | 01-Oct-2026 | 31-Mar-2027 | 182 | Phase 2
13 | Boarding Pass | Boarding Pass Modernization | Sunil Kumar | 01-Oct-2026 | 31-Jan-2027 | 123 | Phase 2
14 | Baggage Visibility | End-to-End Baggage Visibility | Subham Srivastava | 01-Oct-2026 | 28-Feb-2027 | 151 | Phase 2
15 | Auto-Recovery | Rebooking & Refund Automation | Lakshmi Gopalakrishnan | 01-Oct-2026 | 28-Feb-2027 | 151 | Phase 2
16 | Hotel & Voucher | Hotel & Voucher Integration | Lakshmi Gopalakrishnan | 01-Oct-2026 | 31-Dec-2026 | 92 | Phase 2
17 | AI & OCC | AI Decision Engine & OCC Dashboard | Lakshmi Gopalakrishnan | 01-Oct-2026 | 28-Feb-2027 | 151 | Phase 2
18 | Campaign | Paperless Boarding Campaign | Heena Malhotra | 01-Oct-2026 | 31-Mar-2027 | 182 | Phase 2
19 | Connection Tags | Short / Long Connection Tagging | Subham Srivastava | 01-Oct-2026 | 15-Dec-2026 | 76 | Phase 2
20 | Airport APIs | Airport Map APIs (DIAL/MIAL/BIAL) | Subham Srivastava | 01-Oct-2026 | 31-Mar-2027 | 182 | Phase 2
21 | Baggage APIs | Baggage APIs from BRS providers | Randhir Chambail | 01-Oct-2026 | 15-Mar-2027 | 166 | Phase 2
22 | Milestone | Program Kick-off | — | 01-Jul-2026 | 01-Jul-2026 | 1 | Phase 1 | ◆
23 | Milestone | Phase 1 GA – All Quick Wins | — | 30-Sep-2026 | 30-Sep-2026 | 1 | Phase 1 |  |  | ◆
24 | Milestone | Phase 2 Kick-off | — | 01-Oct-2026 | 01-Oct-2026 | 1 | Phase 2 |  |  |  | ◆
25 | Milestone | Phase 2 GA – All Scale Items | — | 31-Mar-2027 | 31-Mar-2027 | 1 | Phase 2 | [8 empty] | ◆
26 | Milestone | Benefits Realization & Closure | — | 30-Apr-2027 | 30-Apr-2027 | 1 | Closure | [9 empty] | ◆
Legend:
Phase 1 (Quick Wins)
Phase 2 (Scale & Differentiate)
◆ | Program Milestone (◆)
Closure / Benefits

## Tech_Dependencies
10. Technical Architecture & Dependencies
10.1 High-Level Architecture (Logical View)
The Connections Enhancement Program will be delivered on four logical layers: (a) Customer interface layer (iOS, Android, Web, WhatsApp, Email, in-airport screens); (b) Orchestration layer (Notification Engine, Decision Engine, Risk Engine); (c) Data & AI layer (Data Lake, Feature Store, ML Models, OCC Dashboard); and (d) Source systems layer (PSS, NetOps / DCS, BRS, Airport APIs, Vernost, Salesforce, Solution Tek). All customer-facing screens and notifications flow from the Orchestration layer, which is fed by the Data & AI layer.
10.2 Technical Dependencies
1. Airport map APIs (DIAL / MIAL / BIAL)
2. Gate and baggage belt information APIs
3. Baggage Reconciliation System (BRS) integration
4. Dynamic QR capability for digital boarding passes
5. Solution Tek and Salesforce integration for hotel and recovery workflows
6. AI-driven decision engine for proactive connection management
7. WhatsApp Business API – capacity & templates
8. PSS PNR-level changes for unified check-in and tagging
9. NetOps real-time feed for connection risk
10. Vernost hotel fulfilment system
10.3 Data Flows
• Inbound: PSS (PNR, sectors, tags), NetOps (real-time flight status, taxi time, OTP), BRS (bag scans, transit status), Airport APIs (gate, belt, map, shuttle), Vernost (hotel inventory), Salesforce (case context).
• Processing: Risk engine (rules + ML), Notification engine (multi-channel), Decision engine (AI-recommended actions for OCC).
• Outbound: App notifications, WhatsApp messages, Email, OCC dashboard, contact-centre knowledge base updates.
10.4 Non-Functional Requirements
• Availability: 99.9% for customer-facing notifications, 99.95% for OCC dashboard during peak hours.
• Latency: ≤ 60 seconds end-to-end from event to customer notification.
• Security: Data encryption in transit and at rest; role-based access controls; DPDP compliance.
• Auditability: All AI decisions logged with input features and recommendation rationale.
• Scalability: Designed to support 5x current connecting passenger volume.

## RACI
Workstream / Action Item | Raja | Summi | Charu | Naresh | Lakshmi | Meenakshi | Heena | Isha | Mahak | Randhir | Vinay | Subham | Nihardip | Swati | Sunil | Chakshu | Jochen
Journey Display – Date changes & duration | A | I | I |  |  |  | C |  |  |  |  | R |  | C | R
Terminal Guidance | A |  | I |  |  |  | C |  |  |  |  | C |  |  | R
Web Check-in – Single click | A |  | C | [8 empty] | C |  | I | R
Airport Maps – Static | A | [5 empty] | C |  |  |  |  | R |  |  | R
Airport APIs – DIAL/MIAL/BIAL | I |  | A | [6 empty] | C |  | R |  | I
Single Boarding Pass | C |  | A | [6 empty] | R |  | R |  | C
Boarding Pass Modernization | A | [5 empty] | C |  |  |  |  | R |  |  | R
Short / Long Connection Tags | A | [8 empty] | R |  | R |  |  | C
Timeline View | A | [5 empty] | C |  |  |  |  | R |  |  | R
Baggage Journey Visibility | C |  | A |  |  | R | [5 empty] | R |  |  | R
Connection Risk Alerts | A |  |  |  | C |  | C |  |  |  |  | R
Auto-Recovery Experience | C |  | A |  | R |  |  | C | C
OCC Dashboard | C |  | A | C | R
AI Decision Engine | C |  | A |  | R | [11 empty] | C
First Port of Entry Guidance | A | [5 empty] | C |  |  |  |  | R |  |  | R
Gate / Belt Notifications | A |  |  |  | R |  | C |  |  |  |  | R
App-First Strategy Campaign | R | A | C |  |  |  | R | [8 empty] | C
Weekly Governance | R | A | I | [10 empty] | R
Baggage APIs |  |  | A |  |  | C |  |  |  | R |  | R
Digital BP Testing (TIGO/LDC) | C | [8 empty] | R | C | R | C
Prototype Build | A | [5 empty] | C |  |  |  |  | R |  |  | R
Legend: | R | Responsible | A | Accountable | C | Consulted | I | Informed

## Governance
12. Governance & Cadence
12.1 Governance Structure (3-Tier)
Tier | Forum | Authority | Frequency
Tier 1 – Sponsorship | Sponsor 1:1s | Final program direction, scope, budget | Ad-hoc + Monthly
Tier 2 – Steering | Steering Committee | Strategic review, escalations, scope changes | Monthly
Tier 3 – Workstream | Workstream Reviews | Delivery decisions, RAID management | Weekly
12.2 Forums & Cadence
Forum | Frequency | Chair | Participants | Purpose | Day / Time | Outputs
Weekly Program Review | Weekly | Swati Kothiyal & Raja Karmakar | All workstream leads | Track tasks, risks, dependencies, escalations | Every Tuesday, 2:00–3:00 PM | Updated RAID, action tracker, decisions log
Daily Standup (Phase 1 Dev) | Daily | Sunil Kumar / Subham Srivastava | Digital dev pods | Sprint progress, blockers | Mon–Fri, 10:00–10:15 AM | Burndown, blocker list
Bi-weekly Digital-CX Sync | Bi-weekly | Charu Verma & Raja Karmakar | Digital + CX leads | Align priorities, customer feedback loop | Every alternate Thursday, 4:00–5:00 PM | Aligned priorities, CX inputs
Monthly Steering Committee | Monthly | Summi Sharma (Sponsor) | Sponsors + Program leads + key stakeholders | Strategic review, scope, budget, escalations | 1st Monday, 11:00 AM–12:30 PM | Sponsor decisions, scope changes
Fortnightly Airport API Sync | Fortnightly | Subham Srivastava | DIAL/MIAL/BIAL leads + Digital | Track API agreements & integration | Friday, 3:00–4:00 PM | Airport-wise tracker
Monthly Risk Review | Monthly | Swati Kothiyal | Workstream owners | Deep-dive on RAID + mitigation | Last Friday, 4:00–5:00 PM | Updated RAID, mitigation plan
Quarterly Business Review | Quarterly | Raja Karmakar | Sponsors + leadership | Benefits realization, NPS, KPIs | End of quarter | QBR deck, benefits report
12.3 Escalation Path
Issues unresolved within 24 hours at workstream level are escalated to Program Leads (Raja Karmakar / Swati Kothiyal). Issues unresolved within 48 hours at Program Lead level are escalated to Sponsors (Summi Sharma / Charu Verma). Any item requiring scope, budget, or compliance approval beyond delegated authority is escalated to EXCO via the next available steering forum, with a SLA of 5 working days.
12.4 Decision Authority
Decision Type | Authority
Scope additions / changes | Sponsors (Summi / Charu) via Steering
Budget reallocation > 10% | Sponsors via Steering
Vendor selection / change | Program Lead + Procurement; Sponsor for > INR 1 Cr
Regulatory deviation / risk acceptance | Sponsors with Legal/Compliance sign-off
Customer-facing language & tone | Raja + Heena (with Sponsor escalation if dissent)
Pilot success / scale decision | Program Lead with Workstream Lead input

## RAID_Log
ID | Type | Category | Description | Impact | Likelihood | Severity | Owner | Mitigation / Action Plan | Target Resolution | Status | Last Updated
R-01 | Risk | API Availability | Delay in DIAL/MIAL/BIAL airport map & gate/belt API agreements | High | High | High | Subham Srivastava | Early engagement, weekly sync, escalation to Charu | 31-Aug-2026 | Open | 25-Jun-2026
R-02 | Risk | Data Quality | BRS data quality and latency variations across stations | High | Medium | High | Randhir Chambail | Define data quality KPIs, fallback messaging | 30-Nov-2026 | Open | 25-Jun-2026
R-03 | Risk | Adoption | Airport scanner adoption of dynamic QR boarding pass | High | Medium | High | Randhir Chambail | Pilot at DEL, partner with airport ops, contingency LDC | 31-Dec-2026 | Open | 25-Jun-2026
R-04 | Risk | Capacity | Salesforce/Solution Tek bandwidth for recovery flows | Medium | Medium | Medium | Lakshmi Gopalakrishnan | Lock dev sprints, secure capacity in advance | 31-Oct-2026 | Open | 25-Jun-2026
R-05 | Risk | Adoption | Customer reliance on counter vs app for recovery | Medium | Medium | Medium | Raja Karmakar | App-first campaign + airport nudges | 31-Jan-2027 | Open | 25-Jun-2026
R-06 | Risk | Regulatory | DGCA / airport authority compliance on unified BP | High | Low | Medium | Randhir Chambail | Legal review; engage DGCA early | 31-Oct-2026 | Open | 25-Jun-2026
R-07 | Risk | Model | AI model accuracy for At Risk/Missed predictions | High | Medium | High | Lakshmi Gopalakrishnan | Shadow-mode first; tune thresholds; human-in-loop | 31-Jan-2027 | Open | 25-Jun-2026
R-08 | Risk | Resource | Stakeholder bandwidth across Digital/CX | Medium | High | High | Swati Kothiyal | Resource plan; weekly governance; escalation matrix | Ongoing | Monitoring | 25-Jun-2026
R-09 | Risk | Partner | Codeshare partner data limitations for connection visibility | Medium | High | Medium | Subham Srivastava | Identify minimum viable data; phase codeshare | 31-Mar-2027 | Open | 25-Jun-2026
R-10 | Risk | Tech | Push notification deliverability on iOS/Android | Medium | Medium | Medium | Subham Srivastava | Multi-channel (push+WA+SMS); delivery KPIs | 30-Sep-2026 | Open | 25-Jun-2026
R-11 | Risk | UX | Information overload in journey timeline view | Medium | Medium | Medium | Sunil Kumar | UX research, A/B, progressive disclosure | 31-Aug-2026 | Open | 25-Jun-2026
R-12 | Risk | Operations | OCC adoption of new dashboard & decision engine | Medium | Medium | Medium | Lakshmi Gopalakrishnan | OCC training; phased rollout; SOP refresh | 28-Feb-2027 | Open | 25-Jun-2026
A-01 | Assumption | Partner | Airports will share APIs within agreed timeline | High | - | - | Subham Srivastava | Confirm via MoUs; track per airport | 31-Aug-2026 | Open | 25-Jun-2026
A-02 | Assumption | Resource | Digital team capacity available as per plan | High | - | - | Swati Kothiyal | Quarterly capacity review | Ongoing | Monitoring | 25-Jun-2026
A-03 | Assumption | Tech | BluChip tier tagging logic exists in PSS/CRM | Medium | - | - | Sunil Kumar | Validate with PSS in week 1 | 15-Jul-2026 | Open | 25-Jun-2026
A-04 | Assumption | Customer | Customers prefer app over web for connections | Medium | - | - | Raja Karmakar | Validate via NPS & adoption metrics | 31-Oct-2026 | Open | 25-Jun-2026
A-05 | Assumption | Tech | WhatsApp Business API throughput sufficient for IROPs spikes | High | - | - | Heena Malhotra | Load test; SLA with provider | 31-Aug-2026 | Open | 25-Jun-2026
A-06 | Assumption | Partner | Vernost remains active partner for hotel fulfilment | High | - | - | Lakshmi Gopalakrishnan | Contract renewal; backup vendor identified | 31-Dec-2026 | Open | 25-Jun-2026
A-07 | Assumption | Process | Network ops feed timely & accurate for risk engine | High | - | - | Subham Srivastava | Data SLA agreement with NetOps | 31-Aug-2026 | Open | 25-Jun-2026
I-01 | Issue | Process | Current check-in is sector-wise; not unified | High | - | High | Sunil Kumar | Build single check-in for entire PNR | 30-Sep-2026 | Open | 25-Jun-2026
I-02 | Issue | Product | No unified boarding pass capability today | High | - | High | Randhir Chambail | Phase 2 dynamic QR initiative | 31-Mar-2027 | Open | 25-Jun-2026
I-03 | Issue | Visibility | Limited baggage visibility post-check-in | High | - | High | Meenakshi Jain | Phase 2 E2E baggage visibility | 28-Feb-2027 | Open | 25-Jun-2026
I-04 | Issue | Process | Manual hotel voucher process during disruptions | High | - | Medium | Lakshmi Gopalakrishnan | Vernost auto integration in Phase 2 | 31-Dec-2026 | Open | 25-Jun-2026
I-05 | Issue | Tech | No AI decision engine in OCC today | High | - | High | Lakshmi Gopalakrishnan | Build AI engine + OCC dashboard | 28-Feb-2027 | Open | 25-Jun-2026
I-06 | Issue | Product | Connection tagging not standardized (short/long) | Medium | - | Medium | Subham Srivastava | Modernize tagging logic Phase 2 | 30-Nov-2026 | Open | 25-Jun-2026
I-07 | Issue | UX | Date change in itinerary not visible to customer | Medium | - | Medium | Sunil Kumar | Phase 1 date change indicator | 31-Jul-2026 | In Progress | 25-Jun-2026
D-01 | Dependency | External | Airport map APIs (DIAL/MIAL/BIAL) | High | - | High | Subham Srivastava | Engagement + contracts | 31-Aug-2026 | Open | 25-Jun-2026
D-02 | Dependency | External | Gate & baggage belt info APIs | High | - | High | Lakshmi Gopalakrishnan | Airport-by-airport rollout | 30-Sep-2026 | Open | 25-Jun-2026
D-03 | Dependency | External | BRS provider integration | High | - | High | Randhir Chambail | Provider shortlist + commercial | 30-Nov-2026 | Open | 25-Jun-2026
D-04 | Dependency | Tech | Dynamic QR capability for unified BP | High | - | High | Randhir Chambail | Build + scanner certification | 31-Dec-2026 | Open | 25-Jun-2026
D-05 | Dependency | Tech | Solution Tek + Salesforce integration for recovery & hotel | High | - | High | Lakshmi Gopalakrishnan | Joint roadmap with IT | 31-Dec-2026 | Open | 25-Jun-2026
D-06 | Dependency | Tech | AI decision engine platform & data lake | High | - | High | Lakshmi Gopalakrishnan | Build/buy decision; platform setup | 31-Jan-2027 | Open | 25-Jun-2026
D-07 | Dependency | Tech | WhatsApp Business API capacity & templates | Medium | - | Medium | Heena Malhotra | Provider SLA + template approval | 31-Aug-2026 | Open | 25-Jun-2026
D-08 | Dependency | Tech | PSS changes for unified PNR check-in | High | - | High | Sunil Kumar | Engagement with PSS team | 31-Aug-2026 | Open | 25-Jun-2026
D-09 | Dependency | Partner | Vernost hotel fulfilment system | Medium | - | Medium | Lakshmi Gopalakrishnan | API integration kick-off | 31-Oct-2026 | Open | 25-Jun-2026
D-10 | Dependency | Internal | Network ops connection-status feed | High | - | High | Subham Srivastava | Data sharing agreement | 31-Jul-2026 | In Progress | 25-Jun-2026

## Resource_Plan
14. Resource & Capacity Plan
14.1 Core Team
Role | Name | Allocation %
Program Lead (Business) | Raja Karmakar | 50%
Program Lead (PMO) | Swati Kothiyal | 50%
Digital Workstream Lead | Sunil Kumar | 75%
App / Platform Engineering | Subham Srivastava | 75%
AI / OCC / Recovery Lead | Lakshmi Gopalakrishnan | 60%
Baggage & Airport APIs | Meenakshi Jain | 40%
Boarding Pass Modernization | Randhir Chambail | 60%
CX Content & Campaign | Heena Malhotra | 50%
Loyalty / Marketing | Chakshu Garg | 25%
Data / AI Platform | Jochen Hoesch | 25%
QA / Testing | TBD | 60%
Vendor – Vernost | Contracted | As needed
Vendor – BRS Provider | Contracted | As needed
Vendor – WhatsApp BSP | Contracted | As needed
14.2 Effort Estimate (Person-months)
Indicative effort estimates by discipline and phase. Baseline numbers to be revised after Phase 1 kick-off.
Discipline | Phase 1 (PM) | Phase 2 (PM) | Total
Product & UX | 6 | 12 | 18
Backend Engineering | 10 | 22 | 32
App Engineering (iOS / Android / Web) | 8 | 16 | 24
Data / AI / Platform | 4 | 14 | 18
QA / Testing | 4 | 10 | 14
CX Content / Campaign | 4 | 6 | 10
PMO / Coordination | 3 | 6 | 9
Total | 39 | 86 | 125

## Budget
15. Budget & Investment Plan
15.1 Indicative Budget
Indicative program budget across both phases. Detailed CapEx / OpEx classification to be finalised with Finance during the first Steering Committee. Figures below are placeholders pending vendor RFPs and final estimates.
Category | Phase 1 (INR Cr) | Phase 2 (INR Cr) | Total | Notes
Internal Engineering |  |  | 0 | Apportioned dev cost
Vendor – BRS APIs |  |  | 0 | Commercial in Phase 2
Vendor – Vernost Auto Hotel |  |  | 0 | API + integration
Vendor – AI Platform |  |  | 0 | Build / buy in Phase 2
Vendor – WhatsApp BSP scale |  |  | 0 | Throughput SLA
Campaign / Creatives |  |  | 0 | Paperless boarding push
Contingency (10%) |  |  | 0 | Risk buffer
Total | 0 | 0 | 0 | Indicative
15.2 Funding Approval Status
Funding approval pending Steering Committee sign-off in the first scheduled Monday review. Procurement engagement for vendor contracts (BRS, AI platform, WhatsApp BSP scale-up) will commence post sponsor approval.

## Comms_Plan
16. Communication & Change Management Plan
16.1 Internal Communication
Audience | Channel | Frequency | Owner
EXCO | Monthly Steering pack | Monthly | Raja Karmakar
Workstream teams | Weekly cadence + Teams channel | Weekly | Swati Kothiyal
OCC | Training + SOPs + dashboard demos | Pre-launch + Monthly | Lakshmi / Naresh
Airport ground staff | Tickers + bulletins + briefings | Phase launches | Heena Malhotra
Contact Centre | Knowledge base + training + scripts | Pre-launch + Monthly | Heena / Vivek
16.2 External Communication
Customer-facing communications will be delivered through the app, email, WhatsApp, website FAQ, and ticker messages. Partner-facing communications (airports, Vernost, BSPs) will be via direct stakeholder briefings led by the relevant workstream owner. All regulatory disclosures will be routed through Legal and the Regulatory Affairs team.
16.3 Change Adoption Levers
• Training: OCC playbook + dashboard training; Contact Centre script refresh; Airport staff briefings.
• SOP Refresh: Disruption Management and Customer Recovery SOPs updated for each phase.
• In-App Onboarding: Coach-marks and first-time-use flows for new features.
• Adoption Campaign: Paperless boarding campaign across app, email, WhatsApp, social.
• Measurement: Adoption dashboards reviewed weekly; iterations planned monthly.

## Quality_Compliance
17. Quality, Compliance & Audit
17.1 Quality Gates
Each phase has explicit entry and exit criteria. No epic moves to scale without pilot success criteria being met. QA sign-off, regression on existing flows, accessibility compliance, and security review are mandatory gate-keepers before GA. Pilot exit criteria are agreed in the workstream review and validated by the Program Lead.
17.2 Compliance
• DGCA – customer communication guidelines during disruption.
• IATA BCBP – boarding pass standards for the unified BP.
• RBI / Payment compliance for the voucher engine and refund automation.
• GDPR / DPDP – data privacy across customer journey data and AI features.
• Audit logs for all AI-driven customer decisions retained per policy.
17.3 Audit Trail
All decisions, scope changes, and exceptions are logged in this workbook (RAID and Milestones tabs) and the monthly Steering minutes. Steering minutes are archived in SharePoint under the program folder for compliance audit reference. The Program Lead (PMO) is custodian of all audit artefacts.

## KPI_Dashboard
18. KPI & Benefits Realization
18.1 Measurement Approach
All KPIs will be instrumented at the time of feature release. Baseline measurements will be taken in Jun – Jul 2026 to enable pre / post comparison. NPS will be measured at the connecting-journey moment via in-app post-flight survey and external panel benchmarks. Operational KPIs will be reported via the OCC dashboard.
18.2 KPI Dashboards
• OCC Operational Dashboard – real-time misconnect, baggage, codeshare risk; AI recommendations.
• CX NPS Dashboard – connecting-journey NPS, themes, and drivers.
• Adoption Dashboard – single check-in, paperless boarding, app-first recovery.
• Cost Dashboard – hotel cost per disruption, refund automation, contact-centre handling cost.
18.3 Benefits Realization Timeline
Quarter | Expected Benefit
Q2 FY27 (Jul – Sep 2026) | Quick-win NPS uplift on visibility and communication; lower 'when is my flight?' calls.
Q3 FY27 (Oct – Dec 2026) | Scale benefits: unified BP pilot, hotel automation GA, paperless campaign launched.
Q4 FY27 (Jan – Mar 2027) | Transformation benefits: AI engine in OCC, baggage visibility GA, paperless adoption ≥ 50%.
Q1 FY28 (Apr – Jun 2027) | Sustained benefits and codeshare-readiness; formal benefits realization review.

## Reporting
19. Reporting & Documentation
• Weekly Status Report – RAID, milestones, KPIs (Swati to circulate every Friday).
• Monthly Steering Pack – progress, decisions, scope, risk (Raja & Swati).
• Quarterly Business Review Pack – benefits, NPS, KPIs (Raja).
• RAID Log Refresh – weekly during program review; monthly deep-dive in Risk Review.
• Milestone Tracker – Milestones tab in this workbook, refreshed every week.
• Audit Pack – Steering minutes, RAID, exceptions, archived in SharePoint.

## Closure_Criteria
20. Program Closure Criteria
1. All Phase 1 and Phase 2 GA milestones achieved and signed off by sponsors.
2. Connecting-journey NPS uplift demonstrated against baseline (+12 pts target).
3. AI Decision Engine operationally adopted in OCC for the agreed scope of cases.
4. Paperless boarding adoption ≥ 50% measured for two consecutive months.
5. All Phase 2 capabilities handed over to BAU operations (CX, OCC, Digital).
6. Post-implementation review completed and signed off by Summi Sharma and Charu Verma.
7. Final benefits realization report archived in SharePoint and shared with EXCO.

## Glossary
Appendix: Glossary
Term | Definition
PSS | Passenger Service System
NetOps | Network Operations
DCS | Departure Control System
BRS | Baggage Reconciliation System
BCBP | Bar-Coded Boarding Pass (IATA standard)
MCT | Minimum Connection Time
OTP | On-Time Performance
OCC | Operations Control Centre
IROPs | Irregular Operations (disruption)
NPS | Net Promoter Score
BLU | BluChip (IndiGo loyalty programme tier)
BSP | Business Service Provider (e.g., WhatsApp BSP)
TIGO / LDC | Airport contingency / Local Departure Control systems
DGCA | Directorate General of Civil Aviation (Indian regulator)
DPDP | Digital Personal Data Protection Act
SLA | Service Level Agreement

## Sign_off
Appendix: Sign-off
By signing below, the named parties acknowledge they have reviewed and approve this Program Plan v1.0 as the baseline for execution. Any deviations from this baseline will be managed via the change-control process and reviewed in the Steering Committee.
Name | Role | Signature | Date
Summi Sharma | Sponsor – SVP ifly & CX | __________________ | __________
Charu Verma | Sponsor – Head of Enterprise | __________________ | __________
|  | __________________ | __________
|  | __________________ | __________